Ongoing Programme of Action

Monitoring Report

July 2008

Prepared by the Secretariat for the Taskforce for Action on Violence within Families

# Contents

Contents	1

Summary	3

Highlights	3

Hotspots	7

Variations	7

Alerts	8

Upcoming Objective deadlines	8

Monitoring Report	9

Three month summaries and milestone updates	11

Leadership	11

1.1  Facilitation of the Ongoing Programme of Action	11

1.1a  Mapping of the Ongoing Programme of Action	12

1.2  Maori Programme of Action	12

1.3  Pacific Programme of Action	13

1.4  Child Maltreatment	14

1.5a  Family Violence Free Workplaces (MSD)	15

1.5b  Family Violence Free Workplaces (ACC)	18

1.5c  Family Violence Free Workplaces (NZ Police)	20

1.6  Iwi Led Crime Prevention	21

1.7  Family Violence Clearinghouse	22

1.8  Case Studies Characterising Good Practice	23

1.9  Maori Research Agenda	24

1.10  Pacific Research Agenda	25

1.11  New Migrant and Refugee Research Agenda	26

1.12  Elder Abuse	27

1.13  Data on NGO Service Delivery	28

Changing Attitudes And Behaviour	31

2.1  Kia Puawai	31

2.2  Improving Attachment	31

2.3  Conduct Disorder / Severe Anti-Social Behaviour	32

2.4  Curriculum Development	34

2.5  Violence in the Media	37

2.6  Campaign for Action on Family Violence	38

2.7  Family Violence Death Review Project	40

Ensuring Safety And Accountability	43

3.1  Family Violence Courts	43

3.2  Protocols for Family Violence Courts	44

3.3  Social Services Supporting Courts	45

Effective Support Services	49

4.1  Maori Service Workforce Development	49

4.2  Pacific Service Workforce Development	50

4.3  Service Demand Data	51

4.4a  Training Our Staff	52

4.4b  Training Our Staff	52

First Programme of Action update	55

How this report works	61

# Summary

The Taskforce for Action on Violence within Families’ (the Taskforce) first programme of action initially consisted of 76 actions, which were later consolidated to 53 actions. A progress summary on these actions is provided towards the end of this report.

The Taskforce’s Ongoing Programme of Action (OPOA) consists of 31 objectives which form the Taskforce’s work programme. To meet each objective, actions and milestones have been identified. This report provides a progress report against the objectives, actions and milestones.

Any variation to objectives or actions requires a formal variation. A variation template must be completed and signed by the appropriate Taskforce member, and then forwarded to the Secretariat. The Secretariat will then forward it on to the Chair of the Taskforce for approval.

Due to feedback received, there have been changes to the format of this Monitoring Report. A section called “Upcoming objective deadlines” has been added. This section highlights objective deadlines that are due in the next two months.  The other change is that the “three month summaries” and the “milestone updates” sections for each objective have been integrated into one section, instead of two separate sections.

For more information on this report, how it is organised and the formal variation process, please refer to the “how this report works” section at the end of the document.

Objective status

| Total number of objectives | 31 |
| --- | --- |
| On track | 21 |
| First phase complete | 6 |
| Variations | 4 pending |
| Alerts | 2 |

## Highlights

This section provides an overview of key Taskforce initiatives for the reporting period of April 2008 to June 2008.

### Leadership

### Maori Programme of Action

Following the Taskforce’s Maori Reference Group (MRG) Whanau Summit, held at Hopuhopu in April 2008, the MRG are conducting regional hui. These hui have been held in May, June and July to inform Maori practitioners, social service and crown agencies, educators and local leaders on the Summit findings, and to also obtain local ideas.  The findings and outcomes from the Summit and regional hui will all be used by the MRG during the development of the Maori Programme of Action.

### Pacific Programme of Action

A draft Pacific Programme of Action has been prepared by the Pacific Advisory Group.  A full briefing will be provided to the Taskforce at the meeting on Wednesday 6 August 2008.

### Domestic Violence Act 1995 review

The Minister of Justice sought Cabinet decisions on legislative amendments to the Domestic Violence Act and related legislation in May 2008.  Cabinet agreed to the proposals set out in the Cabinet papers and the Minister of Justice publicly announced the proposed amendments in June 2008.  A Domestic Violence Amendment Bill is currently being drafted. The Review of the Domestic Violence Act, led by the Ministry of Justice, is not part of the Taskforce's programme of action but aligns closely with the Taskforce’s work.

### Child Maltreatment Prevention

Over the past three months a draft work programme that addresses the child maltreatment aspects of violence within families has been developed. The work programme consists of nine projects and includes actions on all four of the Taskforce fronts. It covers physical, sexual and emotional/psychological abuse and neglect. Its focus is on primary and secondary prevention, rather than responses to actual abuse and neglect, the treatment of the harm done, and prevention of further harm.  There is an emphasis on keeping children safe and secure and supporting their emotional and social development early in life.

Three priorities are proposed:

- Work on ways to reduce the incidence of neglect, including through support of children’s development in early years.

- Work on how to get the best contribution from the health, education and social services sectors.

- Work on ways to work with communities to keep their children safe and secure.

The programme has been prepared by a working group of officials, the Office of the Children’s Commissioner (OCC) and non-government organisation (NGO) representatives. An external advisory group has been established to give advice on the programme and its implementation.

### Changing Attitudes and Behaviour

### Campaign for Action on Family Violence

There were 91 applications for round three of the Community Action Fund which closed on 10 June 2008. In this round, projects that focused on how to make protecting our children everyone’s business were prioritised. Twenty five percent of the applications have a child maltreatment prevention focus. Successful applicants are due to be announced at the end of July 2008. The Campaign is also working closely with Ngati Kahungunu and Amokura which have developed iwi-led family violence prevention strategies. Seven hui have provided Community Action Fund project leaders with the opportunity to share ideas, to increase the connectedness of the national campaign and to plan ahead.

The Stories of Positive Change TV ads from the second phase of the Campaign, will re-screen in the weeks beginning 17 August and 7 September. The Social Change ads (It’s not OK) from the first phase of the campaign will re-screen in the weeks commencing 14 December and 4 January, 2009. The Stories of Positive Change ads will feature again in the week commencing 25 January, 2009.

Data collection for a face-to-face national survey is underway. This survey will specifically explore violence towards women, inter-partner violence and child abuse. Data from this survey will be used to measure the attitudes of New Zealanders towards family violence. The results from the survey will allow for changes in attitudes to be measured over time at a national level and for specific groups of interest.

A community study is also underway. Five communities have been chosen as places where we will undertake an in-depth analysis of the impact of the campaign. Data collection has begun in Porirua and Gisborne. Work will begin soon in Whangarei, Waitakere and Christchurch.

### Family Violence Death Reviews

In April, the Ministry of Health issued a call for nominations for the inaugural members of the Family Violence Death Review Committee.  Nominations closed on 1 May, and 59 applications were received.  Hon Steve Chadwick, Associate Minister of Health, is currently considering the nominations. The Committee will meet for the first time in September/October this year.

### Ensuring Safety and Accountability

### Protection Orders

The Secretariat is preparing a six month report for the Taskforce’s consideration. This report will provide a progress update on implementation of the recommendations from the Waikato University research Living at the Cutting Edge: Women’s Experiences of Protection Orders. A progress report is due to the Minister for Social Development and Employment at the end of August 2008.

### Family Violence Courts

A report summarising key findings from evaluative work undertaken at the Waitakere and Manukau Family Violence Courts has been completed.  The release of this report is being supervised by the Manager, District Courts – Criminal and Youth.  Taskforce members have received a copy of the embargoed report. The release date has not yet been confirmed.

Family Violence Court training

Phase one of the Family Violence Court training has been completed.  The focus of this training has been on the philosophy of Family Violence Courts and the dynamics of domestic violence.  Six workshops have been held at each of the Family Violence Courts.  Court staff, the Judiciary and other key stakeholders (e.g. Police, Corrections, lawyers and NGOs) attended. Feedback from those who have attended has been positive.

Phase two of the training, which focuses on the draft National Operating Guidelines, will be completed by the end of July 2008.

National Operating Guidelines

Consultation on the Family Violence National Guidelines concluded in May 2008.  Responses have been received from a number of key stakeholders, including key NGOs, the Judiciary, Police and internal Court staff.

The Ministry of Justice is considering the feedback and expects to have the finalised guidelines available in August 2008.

### Social Services Supporting Family Violence Courts

In February 2008 the Government provided funding for eight independent victim advocates/support people to support and assist victims of domestic violence in Family Violence Courts. (Six Family Violence Courts are currently operational with two more Courts becoming operational in late 2008/early 2009). The Ministry of Justice (MoJ) has begun work on developing the role of an independent victim advocate/support person to provide support and assistance to victims of domestic violence in all of the Family Violence Courts in conjunction with the Ministry of Social Development (MSD).  Consultation with other agencies and NGOs will take place in August 2008.  The Advocate role will be rolled out in Family Violence Courts from 1 April 2009.

### Effective Support Services

### Pathway to Partnership

The Pathway to Partnership (P2P) Steering Group (made up of representatives from the NGO sector, MSD and MoJ) is advising on the development and implementation of P2P.  The Steering Group includes two representatives nominated by NGO members of the Taskforce for Action on Violence within Families. P2P involves working with community groups so they can deliver high quality services and early support to families, children and young people. The plan will do this by:

- Moving existing essential family, child and youth focused services to full funding by 2011. Over the next six months funding advisors will work with providers to establish their medium term path to full funding over the next four years.

- Providing annual cost adjustment payments. Providers will receive a cost pressure adjustment effective from 1 July 2008.

- Addressing forecast volume increases.

- Focusing more on achieving outcomes and less on outputs.

- Enabling providers to build workforce capability and capacity. Fully funding their contracted essential services will give family violence providers more ability to plan ahead, attract and retain qualified staff and improve service effectiveness.

- Supporting organisations to work more closely together to reduce duplication and get more resources into services.

MSD has been actively working to inform providers about the Pathway to Partnership Plan through the Steering Group, regional forums and with correspondence and will continue to work closely with NGOs to achieve the successful implementation of the Pathway to Partnership Plan.

## Hotspots

This section highlights objectives that are subject to variation or have been identified as areas of risk. All objectives not mentioned in this section are on track to be completed as planned.

### Variations

Variations are formal requests for changes to objectives and/or actions in the Taskforce’s Ongoing Programme of Action. This table includes all historical Variations of objectives from the Ongoing Programme of Action.

| Objective | Title | Variation summary | Status |
| --- | --- | --- | --- |
| 1.10 | Pacific Research Agenda | Changes required to actions, although the objective will remain the same. Further development of the project plan has clarified actions required to achieve Taskforce objectives. | Submitted 23 June. Awaiting approval. |
| 1.9 | Maori Research Agenda | There has been some delay to this project due to availability of specialist Maori contractors, case study organisations and the expert steering group. | Submitted 18 July. Awaiting approval. |
| 3.1 | Family Violence Courts | The objective remains the same. The objective deadline has been missed; the deadline for final establishment of the two Family Violence Courts has been requested to be revised to early 2009. | Due to be submitted in July by the Judiciary, currently being processed by MoJ. |
| 4.2 | Pacific Service Workforce Development | This project plan is now part of the Pathway to Partnership work on workforce provider capacity and capability. Although a project plan was completed within the deadline, the Steering Group has decided that other areas are of first priority. | Submitted 22 July. Currently being processed for approval. |
| Approved variations |
| 3.3 | Social Service Supporting Courts | The objective remains the same, changes to the actions required. The variation was requested due to the need to align with the direction the Chief District Court Judge has set for the Family Violence Courts, and to ensure consistency with a 2008 Budget bid. | Approved 4 April 2008. |
| 2.4 | Curriculum Development | The objective remains the same, changes to the actions required. “Whole school strength based approaches” could not be extended due to an increase in costs for delivery of student wellbeing contracts. The use of this approach is being strengthened by incorporating successful professional learning approaches for student wellbeing in the design and delivery of ongoing professional development contracts. | Approved 28 March 2008. |

### Alerts

This table highlights areas that have been identified as at risk of not being delivered.

| Objective | Title | Issue | Mitigation |
| --- | --- | --- | --- |
| 1.1a | Mapping of the Ongoing Programme of Action | The objective and actions for this work need to be clarified. | The Secretariat has sought input from NGO Taskforce members, and will follow up further. |
| 2.2 | Improving Attachment | A variation may be required as the Auckland DHB has decided not to proceed with the pilot to prevent Shaken Baby Syndrome. Initial scoping highlighted issues with the pilot site. | The Ministry of Health has been approached to fund a regional pilot and is currently considering the possibility. |

### Upcoming Objective Deadlines (next two months)

This table highlights Objective deadlines that are due over the next two months, or that have been completed and further deadlines need to be defined. If deadlines are not likely to be met, agencies should contact the Secretariat to discuss a possible variation.

| Objective | Title | Objective Deadline | Comment |
| --- | --- | --- | --- |
| 1.2 | Maori Programme of Action | Complete to: June 2008 | Complete. Further deadlines on ongoing work need to be defined. |
| 1.3 | Pacific Programme of Action | Complete to: Mid 2008 | About to be completed. Further deadlines on ongoing work need to be defined. |
| 1.4 | Child Maltreatment Prevention | Complete to: 30 June 2008 | Complete. Further deadlines on ongoing work need to be defined. |
| 1.9 | Maori Research Agenda | 31 July 2008 | Variation submitted. |
| 2.6 | Campaign for Action on Family Violence | Complete to: 30 June 2008. Ongoing to 2010. | Complete. Ongoing deadline is 2010. |
| 2.7 | Family Violence Death Review Project | Complete to: 31 June 2008 | Final selection of members likely to be complete in July/August 2008. |
| 4.1 | Maori Service Workforce Development | Complete to: June 2008 | Complete. 71 practitioners have undertaken training. Mauri Ora training is now ongoing. There will be ongoing reporting on this objective, further deadlines need to be defined. |
| 4.2 | Pacific Service Workforce Development | July 2008 | Variation submitted. |

# Monitoring Report

The Detailed Milestone Updates section, outlining progress on each milestone, has now been included with the Three Month Summaries section, which provides an update on work undertaken in the previous three months and work which is upcoming in the next three months.

## Three month summaries and milestone updates

This section provides updates on each milestone, and updates on both work undertaken in the previous three months and work planned for the upcoming three months.

### Leadership

| 1.1 FACILITATION OF THE ONGOING PROGRAMME OF ACTION (OPOA) |
| --- |
| Lead agency | Taskforce Secretariat / All Taskforce agencies |
| Project Manager | Carra Hamon |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) Facilitation, implementation and strategic engagement of the Ongoing Programme of Action for specific groups and across all sectors in New Zealand. Actions include: stewardship of the Ongoing Programme of Action work programme stewardship of children specific work programme stewardship of all other work programmes. |
| Objective deadline | Ongoing |
| Purpose To successfully monitor and ensure implementation of the Ongoing Programme of Action. |
| Key Milestones | Date | Description of Progress |
| 1.1.5 | Protection Orders interim update | May | Complete. |
| 1.1.6 | Monitoring Report for May prepared and sent with 4 June meeting papers. | 20 May | Complete. Included updates actions from First Report. Although the report was completed by 20 May, it was held back and will be sent to the Taskforce with the 6 August meeting papers. |
| 1.1.7 | Protection Orders update to be sent to Minister end August. | 30 August | On track. Draft version will be distributed to the Taskforce in early August. |
| 1.1.8 | Monitoring Report for July prepared and sent with 6 August meeting papers. | 22 July | Complete. |
| Progress to date (previous 3 months work) The new format Monitoring Report is working well. There has been some feedback which has been incorporated into this (July) report. Further feedback is encouraged. An interim update of the Waikato University research on Protection Orders was prepared and is held by the Secretariat. Protocols on distribution of Taskforce information have been finalised and will be circulated to all Taskforce members with 6 August meeting papers. Current ongoing work (next 3 months) Preparing the Monitoring Report for the 1 October 2008 meeting of the Taskforce. Organising the agenda and the papers for the next Taskforce meeting and assisting in the organisation of the Ministerial Team and Multi-Party Group meetings. Facilitating and writing the Protection Orders report due to the Minister for Social Development and Employment at the end of August 2008. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 1.1a MAPPING OF THE ONGOING PROGRAMME OF ACTION (OPOA) |
| --- |
| Lead agency | NGOs |
| Contributors |  |
| Project Manager |  |
| Objective and actions (as per Work Programme) Actions include: Ongoing Programme of Action mapped to its outcome. |
| Objective deadline | TBC |
| Purpose TBC |
| Key Milestones | Date | Description of Progress |
| 1.1a.1 | Definition of this objective | 1 July 2008 | NGO Taskforce members have been approached to discuss this objective. |
| Alert: Next steps to be confirmed. |

| 1.2 MAORI PROGRAMME OF ACTION |
| --- |
| Lead agencies | Maori Reference Group (MRG) Ministry of Social Development |
| Contributors | Te Puni Kokiri, NGOs |
| Project Manager | Ann Dysart (MSD) |
| First Programme of Action reference | Action 7 |
| Objective and actions (as per Work Programme) A Programme of Action focused on eliminating violence in Maori whänau is developed. Actions include: developing a Maori Programme of Action ensuring the leadership and ownership of the actions at all levels of Te Ao Maori. |
| Objective deadline | June 2008 |
| Purpose To develop a process and plan that engages all areas of Te Ao Maori in owning and addressing the issues of Family Violence and Child abuse. |
| Key Milestones | Date | Description of Progress |
| 1.2.3 | Local regional hui with Maori family providers and practitioners | April / May 08 | A good percentage of regional hui have been completed as at 30 June. The remaining hui will be fully completed by the end of July. |
| 1.2.4 | Launch Maori Programme of Action (MPOA). | June 08 | A draft MPOA has been completed, and will be presented to the first available Taskforce meeting on 6 August. This milestone date will be revised once the MPOA has been finalised, to show when the launch is likely to be. |
| 1.2.5 | Work towards establishing an action plan for 08/09 and priorities for next five years | TBC |  |
| Background The Taskforce’s MRG is developing a Maori Programme of Action (MPOA). Progress to date (previous 3 months work) Whanau Summit was successfully completed with findings and outcomes having been disseminated to attendees at regional hui. Those completed regional hui have shown strong discussions taking place with valuable outcomes that have been incorporated into the MRG’s draft MPOA. Current ongoing work (next 3 months) Finalisation of remaining regional hui. Finalisation of MPOA. Timing / Ongoing / Recommendations / Conclusions Status = First phase achieved. The next deadlines to be defined from MPOA once it is finalised. |

| 1.3 PACIFIC PROGRAMME OF ACTION |
| --- |
| Lead agency | Pacific Advisory Group (PAG) Ministry of Social Development |
| Contributors | Ministry of Pacific Island Affairs, NGOs |
| Project Manager | Liz Tanielu (MSD) |
| First Programme of Action reference | Action 7 |
| Objective and actions (as per Work Programme) Programme of Action focused on eliminating violence in Pacific families is developed. Actions include: develop a Pacific Programme of Action. |
| Objective deadline | Mid 2008 |
| Purpose To articulate the status of Family Violence as it impacts on Pacific People and outline specific actions to address it. |
| Key Milestones | Date | Description of Progress |
| 1.3.2 | Stakeholder Meetings for input into POA | March 08 | Consultation begun. |
| 1.3.3 | Final POA | June 08 | A draft Pacific POA has been completed and will be presented at the 6 August Taskforce meeting. |
| 1.3.4 | Release of Pacific POA | TBC |  |
| Progress to date (previous 3 months work) A draft Pacific POA has been developed. Comments from stakeholders have been incorporated. Current ongoing work (next 3 months) The Taskforce will be briefed at the next meeting in August on the draft Pacific POA and to discuss next steps. The PAG will continue to provide advice on projects within the OPOA, including Pathways to Partnership, Changing Attitudes and Behaviour, the Pacific Research Agenda and Child Maltreatment Prevention. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 1.4 CHILD MALTREATMENT |
| --- |
| Lead agency | Office of the Children’s Commissioner |
| Contributors | MSD, NGOs, Justice, Health, Education, Police |
| Project Sponsor | Dr Cindy Kiro |
| Project Manager | John Angus / Ruth Palmer (MSD) |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) A long term plan is developed for government’s work on addressing child maltreatment (including child sexual abuse) within families. Actions include; assess current work on prevention and reduction of child sexual abuse review existing literature develop a research agenda link to the Taskforce strategic research agenda for family violence prevention include children with disabilities within this work plan future work ensure ongoing communications between Taskforce and the Taskforce for Action on Sexual Violence. |
| Objective deadline | 30 June 2008 |
| Purpose Child maltreatment in New Zealand has been difficult to quantify and fully understand. General consensus holds that child maltreatment occurs predominantly within families. This work will develop an integrated, cross government approach to work on child maltreatment which has attached to it a growing evidence and knowledge base. |
| Key Milestones | Date | Description of Progress |
| 1.4.4 | Draft work programme developed | June 2008 | Completed. Draft work programme completed and sent to Taskforce (TF) in early July for feedback. A final version will be presented to the August TF meeting. The External Advisory Group was confirmed in June, and has had input into this work programme. |
| 1.4.5 | Work programme agreed | August 2008 | Due to be presented to 6 August TF meeting for agreement (earliest meeting available). |
| 1.4.6 | Further milestones developed | Sept 2008 | NOTE: When programme is agreed further milestones will be developed. |
| Background The Ongoing Programme of Action, includes developing a work programme on child maltreatment (including child sexual abuse) that: focuses on improving outcomes for children takes account of the different types of child maltreatment identifies priority areas where the Taskforce can make a difference. Progress to date (previous 3 months work) The Working Group was established in May and has met weekly, and developed a draft work programme for consideration by the Taskforce. The External Advisory Group (EAG) has been set up. It has had input into the draft work programme and it is due to meet on 22 July. The EAG will continue to be available for expert advice throughout 2008 - 2009 A draft work programme has been prepared. It consists of nine specific areas of work cross the four fronts that the Taskforce programme. It proposes three priority areas of action: neglect, education, health and social services sector contributions, and working with communities to keep children safe and secure. There has been consultation with the NGO Alliance, FSNAC, MRG, PAG and within the Ministries of Social Development, Health and Education. We have discussed the coverage of child sexual abuse with the Taskforce for Action on Sexual Violence. A report on the draft work programme has been prepared and sent to Taskforce members for their initial comments before a final proposal is prepared for consideration by the Taskforce 6 August 2008. Current ongoing work (next 3 months) Developing more detailed plans for the agreed work programme projects Commencing work on the agreed 2008 – 2009 outputs. Timing / Ongoing / Recommendations / Conclusions Status = Completed to 30 June 2008. Next deadlines to be defined from work programme. |

| 1.5a FAMILY VIOLENCE FREE WORKPLACES (MSD) |
| --- |
| Lead agency | MSD |
| Contributors | ACC, Police, NGOs |
| Project Manager | David Dick |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) Family Violence -Free Workplaces are developed and implemented through HR policy – link to Campaign, model for other agencies, role model for public and other workplaces. Actions include: develop policy put in place tools and resources training of contact people/family violence co-ordinators implementation develop a model for replication in the public sector and private sector |
| Objective deadline | May 2012 |
| Purpose Family Violence Free Workplaces means staff in those workplaces are aware and supported around issues to do with family violence. These workplaces are expected to provide low cost high impact prevention and recovery opportunities for members of the workplace who are affected by family violence. They may be victims, observers or perpetrators. Implementing Family Violence Free Workplaces is expected to decrease workplace stress, and increase workplace productivity by empowering and supporting victims and observers of family violence and channelling perpetrators through appropriate channels to help them change their behaviour. |
| Key Milestones | Date | Description of Progress |
| 1.5a.2 | Policy development | Dec 2008 | Draft completed – being progressed through approval processes. Seeking further consultation – Dec 2008 is the revised milestone date. |
| 1.5a.3 | Establish internal steering group to oversee Family Violence initiatives | Dec 07 | Completed. |
| 1.5a.4 | Manager guidelines developed to support policy. Published on MSD intranet site | See 1.5a.2 | Draft guidelines developed and to be progressed through approval process. Seeking further consultation – see 1.5a.2 for revised date. |
| 1.5a.5 | Raising Awareness of Family Violence Regional info sessions | Dec 2008 | Exploring need and options for delivery of regional information sessions (links to 1.5a.7) possible web based tools. Revised milestone date. |
| 1.5a.6 | Providing accessible information and resources Provide informational resources for workplaces – such as posters, booklets, toolkits | Dec 2007 | Complete. Resources from the Family Violence (FV) Campaign distributed to business units. |
| 1.5a.7 | Tools and resources address concerns about Family Violence counselling services available through current EAP provider Explore the development of web-based family violence resources for the workplace | Oct 2007 2009 | Completed. A new EAP provider commenced on 1 October 2007. Family violence issues were included as part of RFP process. Will monitor to identify if issues regarding availability of family violence counselling services have been resolved. Still in earlier exploration stages. Subject to potential joint development between Family and Community Services, Preventing Violence in the Home (PVH) and funding. |
| 1.5a.8 | Training Deliver additional training programmes for key support people and all staff as required | As required | To be programmed subject to demand. Provided by PVH. |
| 1.5a.9 | Peer support framework developed approval developed pilot track and assess roll-out to other areas. | Dec 2008 | Complete. The Work and Income service line peer support programme launched in Dec 2007 to provide in-house support on family violence and information services. A review meeting was held in June 2008. As a result there has been some fine-tuning of the programme and the number of staff offering peer support is being reviewed. Next review meeting scheduled for Nov 2008. Child, Youth and Family (CYF) considering as part of broader peer support framework for staff. |
| Overall Context The current HR plan to support the goal of becoming a family violence free workplace involves a longitudinal approach founded on raising and maintaining staff awareness of family violence - the workplace impacts and supports. This work involves developing a family violence policy and initial support mechanisms (eg information and resources, and referral options through the Employee Assistance Programme provider). The next stages involve identifying and building further support mechanisms for staff and managers. Underpinning this work is the ongoing awareness raising initiatives which include information sessions, posters, and “family violence” messages through Corporate communication channels. Consistent with Te Rito principles, MSD HR will also continue to enhance initiatives as information and better ways of working are identified. This will involve testing or piloting some initiatives (such as peer support groups) and information sharing across other Taskforce contributors (ACC and NZ Police). 1.5a.2 Policy development Background The purpose of the family violence policy is to raise awareness of the impact of family violence in the workplace and to provide and raise awareness of the support mechanisms for employees who are experiencing family violence, want assistance to help others, or want assistance to stop their violence. Progress to date (previous 3 months work) MSD has invited the PSA to review the draft policy, and subject to their input we will continue to progress the sign-off process. Current ongoing work (next 3 months) Progress the draft policy through the approval process and plan for its implementation. Timing / Ongoing / Recommendations / Conclusions Status = Ongoing. Revised milestone date of Dec 2008 in order to undertake further consultation. 1.5a.3 Establish internal steering group to oversee Family Violence initiatives Completed – An internal Steering Group to guide the HR Family Violence initiatives has been established. Timing / Ongoing / Recommendations / Conclusions Status = Complete. 1.5a.4 Manager guidelines developed to support policy Progress to date (previous 3 months work) The Manager Guidelines have been developed as a companion resource to the family violence policy and will be implemented once the family violence policy has been approved. Current ongoing work (next 3 months) No further developments this quarter. Will be progressed in conjunction with 1.5a.2 Timing / Ongoing / Recommendations / Conclusions Status = Ongoing. Subject to 1.5a.2. 1.5a.5 Regional information sessions Background The information sessions are part of the broader “family violence awareness raising” activities. Current ongoing work (next 3 months) Subject to needs analysis and identification of options to deploy information sessions sustainably. Exploring delivery options for family violence information sessions for regional staff. Canvas demand and deliver regional sessions accordingly. This links with 1.5a.7 (tools and resources) and the possible development of online resources. Timing / Ongoing / Recommendations / Conclusions Status = Ongoing. Revised milestone date of Dec 2008. 1.5a.6 Providing accessible information and resources Progress to date (previous 3 months work) Information and links are on the MSD intranet. Information on the Work and Income Peer Support Network (refer 1.5a.9) is also on the intranet. Family violence posters (from the Campaign) are displayed in the entrance way to the Bowen State building in National Office. Current ongoing work (next 3 months) A communication plan for 2008 is being developed, which will identify opportunities to raise awareness and maintain the profile of violence family-related initiatives. Timing / Ongoing / Recommendations / Conclusions Status = Complete. 1.5a.7 Tools and resources Ongoing (long term) Exploring options for the development of web-based family violence resources for the workplace, with implementation in 2009. Timing / Ongoing / Recommendations / Conclusions Status = on track 1.5a.8 Training Progress to date (previous 3 months work) No specific training has taken place over the previous three months. Current ongoing work (next 3 months) Training will be planned and delivered subject to demand. Nothing currently confirmed. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 1.5b FAMILY VIOLENCE FREE WORKPLACES (ACC) |
| --- |
| Lead agency | Accident Compensation Corporation |
| Contributors | MSD, Police, NGOs |
| Project Manager | Danielle George |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) Family Violence Free Workplaces are developed and implemented through HR policy – link to Campaign, model for other agencies, role model for public and other workplaces. Actions include: develop policy put in place tools and resources training of contact people/family violence co-ordinators implementation develop a model for replication in the public sector and private sector. |
| Objective deadline | December 2008 |
| Purpose Family Violence Free Workplaces means staff in those workplaces are aware and supported around issues to do with family violence. These workplaces are expected to provide low cost high impact prevention and recovery opportunities for members of the workplace who are affected by family violence. They may be victims, observers or perpetrators. Implementing Family Violence Workplaces is expected to decrease workplace stress, and increase workplace productivity by empowering and supporting victims and observers of family violence and channelling perpetrators through appropriate channels to help them change their behaviour. |
| Key Milestones | Date | Description of Progress |
| 1.5b.2 | Release of Family Violence Policy | 15 Nov 2007 | Complete |
| 1.5b.3 | HR Co-ordinator skills development | TBC | Delayed as initial half-day pilot run by PVH did not meet the needs of the organisation. Alternative supplier or modifications to PVH module under investigation. In the interim, in conjunction with an external provider, ACC have developed a support framework for staff that may be experiencing family violence while further work is done to develop more suitable and appropriate resources. Milestone date to be confirmed. |
| 1.5b.4 | Training programmes and managers’ guides | 31 Oct 2008 | Delayed, as above. Revised milestone date. |
| 1.5b.5 | Policy and guideline refresh | 31 Oct 2008 | Complete. Refresh launch of policy and guidelines, Family Violence Support also launched as part of ACC’s Staff Wellbeing programme in February 2008. |
| 1.5b.7 | FV and FW Support programme | 31 July 2008 | External support programme developed to provide 1:1 support for staff, HR team and managers. Website and service launches 31 July 2008, including access via text service. |
| 1.5b.6 | Family Violence Free Workplaces (FVFW) established across ACC | 31 Dec 2008 | On track for fully embedded across ACC by end of 2008 |
| Progress to date (previous 3 months work) A refresh launch of the Family Violence policy and guidelines took place in February 2008. ACC continues to work with PVH to adapt the tools used in training for human resources staff within the MSD so they are relevant for ACC. An initial half-day pilot training by PVH took place in early 2008, however this was found not to meet the needs of the organisation. An alternative provision for support has been identified and will be implemented in July. Current ongoing work (next 3 months) Continuing work on developing training for staff. This includes additional resource development. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 1.5c FAMILY VIOLENCE FREE WORKPLACES (NZ Police) |
| --- |
| Lead agency | New Zealand Police |
| Contributors | MSD, ACC, NGOs |
| Project Manager | Carol Train |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) Family Violence -Free Workplaces are developed and implemented through Police HR policy – link to Campaign, model for other agencies, role model for public and other workplaces. Actions include: develop policy put in place tools and resources training of contact people/family violence co-ordinators implementation develop a model for replication in the public sector and private sector. |
| Objective deadline | May 2012 |
| Purpose Family Violence Free Workplaces will raise the awareness of staff in the Police about family violence and provide support where appropriate. Police staff may be victims, observers or perpetrators of family violence. Implementing Family Violence Workplaces is expected to decrease workplace stress, and increase workplace productivity by empowering and supporting victims and observers of family violence and channelling perpetrators through appropriate channels to help them change their behaviour. |
| Key Milestones | Date | Description of Progress |
| 1.5c.1 | Policy developed and agreed | Dec 2008 | On track, meeting with MSD as they have progressed this project further. |
| 1.5c.2 | Training and resource developed | Dec 2009 | On track |
| 1.5c.3 | Communications package completed | Jan 2010 | On track |
| 1.5c.4 | Training Delivered in all Districts | Dec 2010 | On track |
| 1.5c.5 | Family Violence Free Workplaces established in Police | TBC | On track |
| 1.5c.6 | Evaluation of Police model | Dec 2011 | On track |
| 1.5c.7 | Finalise Blueprint for implementing Family Violence Free Workplaces in public, private and non-government sectors | May 2012 | On track |
| Progress to date (previous 3 months work) A discussion paper with overview of policy and discussion pointers has been prepared. Police HR met with Manager Wellness and Manager Welfare Officers to discuss level of involvement from both in writing of policy. A proposed working group has been approved by the General Manager of HR. It is proposed that the working group will include representation from: - Equity & Diversity - Family violence - Policy - Wellness - Welfare - District – Waikato. Current ongoing work (next 3 months) Working group members will be confirmed. A meeting will be organised for the working group to discuss the policy. A draft policy will be written. HR will commence consultation on the draft policy. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 1.6 IWI-LED CRIME PREVENTION |
| --- |
| Lead agency | New Zealand Police |
| Contributors | Iwi, NGOs, Te Puni Kokiri |
| Project Manager | Wally Haumaha |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) Iwi-led crime prevention plans which have a focus on the prevention of family violence Actions include: provide support to iwi to develop plans Iwi-led crime prevention strategies developed in accordance with each iwi identified needs, values and timeframes. |
| Objective deadline | This is an iterative and evolving process that is being driven by iwi. Precise deadlines are neither available, nor appropriate at this stage. |
| Purpose In absolute numbers, a high number of Maori churn through the criminal justice system every year. A new framework for action is being developed by Maori with assistance from officials. That new framework is Iwi-led Crime Prevention Plans (ICPPs). ICPPs take a long-term, incremental approach to improving Maori criminal justice outcomes. They are led by iwi, with assistance from officials. |
| Key Milestones | Date | Description of Progress |
| 1.6.1 | Iwi to populate their crime prevention plan templates | No deadline | On track |
| 1.6.2 | Officials to condense those templates into A3 summaries | No deadline | Pending |
| 1.6.3 | Summaries to be presented back to iwi for confirmation | No deadline | Pending |
| 1.6.4 | Ministerial briefing paper to Ministers of Justice, Police and Maori Affairs | March 2008 | Complete |
| Background recent work (2007/2008) Police and Te Puni Kökiri have been supporting iwi with the necessary tools to develop and design their own Plans. The type of support provided includes: providing Police intelligence to iwi groups that enable iwi to understand the crime problems and profiles of Mäori (offenders and victims) within their geographical areas. providing specialised trained staff who are able to take iwi through a formal problem solving approach to crime prevention crime prevention methodology training in SARA and POP models providing draft Iwi Crime Prevention Plan templates and Guidance Notes for preparation of the Iwi Plans funding writers nominated by iwi to begin drafting iwi-specific crime prevention plans. Progress to date (previous 3 months work) first plan being finalised and implemented (for Te Arawa). Current ongoing work (next 3 months) Police are continuing to work with iwi in six Police districts (through individual workshops) to support them in "trailblazing" this work, while work continues across the remaining six Police districts with ongoing dialogue between Police and major iwi groups. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 1.7 FAMILY VIOLENCE CLEARINGHOUSE |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | Families Commission, NGOs |
| Project Manager | Jeff Sheerin |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) The New Zealand Family Violence Clearinghouse (NZFVC) is enhanced to ensure its efficacy and to become the independent, sustainable, comprehensive one-stop shop for national and international information on family violence. Actions include: develop a model and systems which optimise the operations of the NZFVC. |
| Objective deadline | June 2009 |
| Purpose To review NZ Family Violence Clearing House activities and services and develop a strategy for moving forward. |
| Key Milestones | Date | Description of Progress |
| 1.7.1 | Negotiate contract with Canterbury University | 30 Jan 2008 | Negotiations concluded April 2008. A variation to the contract extending it by two months to 31 August 2008 has been agreed and signed by parties. |
| 1.7.2 | Scope redevelopment of NZFVC project, identify requirements and develop strategy | September 2008 | Now underway. Was some delay, the September 2008 revised milestone date is three months later than the original date. |
| 1.7.3 | Develop 2-5 year strategy | 30 June 2009 | This work is dependent on human resource availability. Milestone date now reflects realistic timeframe. |
| 1.7.4 | Develop project plan and secure funding | September 2008 | Now underway on basis of planning for long term sustainable Clearinghouse website from 1 March 2009. |
| 1.7.5 | Implement new clearinghouse website and service | 28 February 2009 | Planning now underway and work definitions document being developed with MSD IT. February 2009 is revised milestone date. |
| Progress to date (previous 3 months work) 1.7.1 - The contract for the provision for a NZFVC for the 2007-2008 year was approved and signed by MSD and the University of Canterbury. A further variation to the contract, providing for an additional two months of services for the Clearinghouse, to 31 August 2008 has now been signed. Management and the NZFVC team have determined an option to provide an interim service to maintain the Clearinghouse while development of a new NZFVC takes place from 1 September 2008. 1.7.2 - Work has commenced on gathering requirements for a new NZFVC on the basis of bringing the IT operations for the NZFVC in-house to MSD. Development work will also include developing users needs and ideas around the look and feel of a new NZFVC. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 1.8 CASE STUDIES CHARACTERISING GOOD PRACTICE |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | NGOs, Justice, Police |
| Project Manager | Dorothy Adams |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) Case studies characterising good practice in service aimed at eliminating family violence are developed and made publicly available. Actions include: scope and identify existing good practice models record the characteristics of their success index and deposit in Family Violence Clearinghouse. |
| Objective deadline | October 2008 |
| Purpose To describe and generalise good practice principles as they apply to family violence prevention. |
| Key Milestones | Date | Description of Progress |
| 1.8.1 | Identification of case study subjects | April 2008 | Completed |
| 1.8.2 | Draft case studies | Sept 2008 | On track. Data collection underway. |
| 1.8.3 | Final case studies | Oct 2008 | On track |
| Background Current evaluative activities will be used to identify good practice models. The project will commence by drawing on one of the evaluative activities that support the Campaign for Action on Family Violence (the Campaign). The case studies will therefore focus on the practice of family violence prevention through social marketing. The aim of the evaluation project is to investigate and illustrate the impact of the Campaign on selected communities. It will focus on collecting information on observable and recorded changes relating to family violence over time in selected communities. As part of this evaluation two case studies will be produced that illustrate and explain “significant changes” arising from the Campaign. Progress to date (previous 3 months work) Selection of community researchers is underway. Data collection has commenced in two communities. Current ongoing work (next 3 months) All community researchers will be identified and data collection will begin in remaining communities. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 1.9 MAORI RESEARCH AGENDA |
| --- |
| Lead agency | Te Puni Kökiri |
| Contributors | MRG, MSD, Families Commission, NGOs |
| Project Manager | Te Atarangi Whiu |
| First Programme of Action reference | New initiative |
| Objective and actions (as per Work Programme) Improve our understanding of the nature of family violence in whänau Mäori and successful models of prevention and intervention. Actions include: review existing literature develop a research agenda link to the Taskforce strategic research agenda for family violence prevention recommend further action. |
| Objective deadline | 5 September 2008 [Variation request submitted] |
| Purpose To increase the evidence base by providing case studies of a minimum of three Maori designed, developed and delivered programmes. |
| Key Milestones | Date | Description of Progress |
| 1.9.1 | Progress Report | 31 Jan 08 | Completed. Scope of project defined. Three key outputs. |
| 1.9.2 | Key findings presentation to Taskforce meeting | 6 Aug 08 | Presentation/information to Taskforce currently under development. |
| 1.9.2 | Final Report | 5 Sep 08 | Strong progress made, delays due to provider availability and consultation. |
| Background Te Puni Kōkiri is working to identify current information regarding family violence for Maori, and looking at culturally distinct models of prevention and intervention for Maori. It is expected that an agenda for research will emerge from this work. Three key outputs for this work were identified: Output One: A literature review intended to identify current information on Maori family violence; information gaps; inconsistencies; and themes within the literature on family violence and Maori. Output Two: A case study analysis of existing Maori designed, developed and delivered initiatives that address family violence. Output Three: A summative report that analyses output one and two and identifies research priorities to form a Maori Research Agenda. Progress to date (previous 3 months work) Significant progress on the literature review and case studies has occurred. All interviews and research have been completed for the case studies of three initiatives, and the reports are in draft form. An analysis hui was held on 7 July 2008 with an external expert reference group to look at early findings. The draft framework of the Summative Report is complete. Consultation has also occurred with the Families Commission with regards to their Research Agenda project. These projects are distinct but complementary. Current ongoing work (next 3 months) The literature review and case study reports will be finalised. The Summative report will be completed. This will include analysis of the literature review with the case studies, as well as identifying research gaps. Consultation with sector experts is ongoing. Timing / Ongoing / Recommendations / Conclusions Status = Variation submitted for delayed timing. |

| 1.10 PACIFIC RESEARCH AGENDA |
| --- |
| Lead agency | Ministry of Pacific Island Affairs (MPIA) |
| Contributors | PAG, MSD, Families Commission, NGOs |
| Project Manager | David Schaaf |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) A Variation has been submitted to the Chair of the Taskforce. Content may differ in this objective from previous reporting. |
| Improve our understanding of the nature of family violence in Pacific families and successful models of prevention and intervention. Actions include: finalise project plan consultation with Pacific Advisory Group consultation with other Pacific stakeholders development of report including identification of Pacific Family Violence Research priorities development of a research agenda linked to the TF strategic research agenda recommending further action. |
| Objective deadline | Final deadline to be confirmed |
| Purpose To develop an understanding of Pacific family violence research priority topics and the issues which surround Pacific family violence research. |
| Key Milestones | Date | Description of Progress |
| 1.10.1 | Finalise project plan | April 2008 | Complete. Project plan finalised, stakeholder discussions completed. |
| 1.10.2 | Consult with Pacific Advisory Group | June-July 2008 | Initial discussion has commenced. |
| 1.10.3 | Consult with other Pacific stakeholders | August 2008 | Not yet commenced. |
| 1.10.4 | Completion of report | September 2008 | Not yet commenced. |
| Background The Pacific Family Violence Research Agenda will sit within a Pacific Research Agenda. Progress to date (previous 3 months work) MPIA met further with the Families Commission, MSD and the Pacific Advisory Group (PAG) to discuss the development of a Pacific research agenda to ensure it is in line with the Family Violence Research Strategy, and complements to the Pacific Programme of Action. Project specifications have been finalised. The Ministry has also had initial discussions with PAG about broad research areas of interest. Current ongoing work (next 3 months) The MPIA will consult with PAG again in late July about what research on Pacific family violence is needed both now and in the future. The Ministry will also go through a prioritisation exercise with PAG. A wider stakeholder group will also be brought together for consultation. A report will be developed which will outline the issues associated with Pacific family violence research and culminate in the development of Pacific family violence research priority topics. Timing / Ongoing / Recommendations / Conclusions Status = some delay. Awaiting approval of the Variation submitted 23 June 2008. |

| 1.11 NEW MIGRANT AND REFUGEE RESEARCH AGENDA |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | NGOs |
| Project Manager | Dorothy Adams |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) Improve our understanding of the nature of family violence in new migrant and refugee families and successful models of prevention and intervention. Actions include: review existing literature develop a research agenda link to the Taskforce strategic research agenda for family violence prevention recommend further action. |
| Objective deadline | To be provided after the scoping phase |
| Purpose A statement of purpose will be developed in the scoping phase. |
| Key Milestones | Date | Description of Progress |
| 1.11.1 | Synthesis of literature | April 2008 | Annotated bibliography completed. |
| 1.11.2 | Scoping paper | June 2008 | Delayed. See note below regarding ongoing work (next 3 months). Milestone date not yet revised. |
| Progress to date (previous 3 months work) An annotated bibliography has been completed. Current ongoing work (next 3 months) Annotated bibliography will be sent to a small group of MSD officials to progress the research agenda regarding the following topics of interest for this project: the nature of family violence in new migrant and refugee families successful models of prevention successful models of intervention. A scoping paper outlining the completion of this project will be developed from that discussion. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 1.12 ELDER ABUSE |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | NGOs |
| Project Manager | Cilla Corlett |
| First Programme of Action reference |  |
| Objective and actions (from work programme) Improve our understanding of the nature of elder abuse and successful models of prevention and intervention. Actions include: review existing literature develop a research agenda link to the Taskforce strategic research agenda for family violence prevention recommend further action. |
| Objective deadline | Final deadline to be confirmed |
| Purpose/Expected Outcome: Improved decision-making about viable programme and service delivery to eliminate elder abuse and neglect within the family setting. |
| Key Milestones | Date | Description of Progress |
| 1.12.2 | Develop a research agenda | 30 July 2008 | On track. MSD is currently working with Age Concern and a selected group of stakeholders in drafting recommended directions for elder abuse and neglect (with a recommended research agenda included as part of this). |
| 1.12.3 | Link to the Taskforce strategic research agenda for family violence prevention | Ongoing | Although the proposed programme of action on EAN will encompass all forms of elder abuse and neglect across all settings, not just within families, strong links will be made between the EAN research strategy and the Taskforce strategic research agenda for family violence prevention in the above work. On track. |
| 1.12.4 | Recommend further action | - May 2008 - August 2008 - Sep 2008 | Complete. Reported to Minister seeking approval of a proposed work programme, timeline and governance arrangements for working towards developing a national action plan for elder abuse and neglect. - Complete consultation with sector on issues and priorities. On track - Report to Minister of SDE and to Taskforce (for Taskforce October 2008 meeting) with recommended priorities for action. |
| Background 1.12.2 and 1.12.3 The research agenda on Elder Abuse and Neglect (EAN) will be informed by the environmental scan (see 1.12.4 below). 1.12.4 Following a joint Age Concern NZ/MSD presentation to the Taskforce in April 2006 on a proposed national action plan/strategy on EAN, MSD and Age Concern have commenced an environmental scan with the view to preparing an ongoing national programme of action on EAN Policy. Progress to date (previous 3 months work) Cross-MSD reference group for EAN Policy established. Draft environmental scan/working paper completed (Age Concern NZ and MSD). A work programme for identifying priorities for further action on elder abuse and neglect prevention was sent to the Minister of SDE early June. Current ongoing work (next 3 months) Complete consultation with sector on issues and priorities. Report to Minister of SDE and to Taskforce (for Taskforce October 2008 meeting) on actions undertaken to date, and present an outline of the proposed priorities for further action. Timing / Ongoing / Recommendations / Conclusions Status = On track. Deadline to be confirmed. |

| 1.13 DATA ON NGO SERVICE DELIVERY |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | NGOs, ACC, Justice, Police, Health |
| Project Manager | Dorothy Adams |
| First Programme of Action reference |  |
| Objective and actions (from work programme) High quality data available about services delivered by, and on the demand for, NGO and agency family violence services. Actions include: develop systematic and accurate data on services |
| Objective deadline | To be confirmed after scoping work completed |
| Purpose A purpose statement will be derived from the scoping study. This work is aligned with the “Pathway to Partnership” initiative. |
| Key Milestones | Date | Description of Progress |
| 1.13.1 | Scoping study and project plan | July 2008 | On track. Revised milestone date required for next report, as per below. |
|  | No further milestones provided as yet |  |  |
| Background The initiative to support a sustainable NGO social service sector (part of Pathway to Partnership) will roll-out a sustainable funding path for essential NGO services for families, children and young people. All essential Family Violence prevention services will be part of this initiative. As part of implementing this project, a data monitoring system that focuses on outcome measures will be developed in collaboration with the sector and implemented. This monitoring system will provide high quality data about service outcomes. Current ongoing work (next 3 months) A Terms of Reference for the development of a data collection system has been approved by the Pathway to Partnership Management Group. During the next 3 months the Monitoring and Evaluation project will: conduct analysis of data collection tools currently in use by both MSD and NGOs capture the reporting and monitoring information requirements, data available (quality and depth) and current data collection methods from both MSD and NGOs determine the data quality and depth required for use by MSD determine requirements for reporting and evaluation systems support (linked to the Outcomes Framework Project) work with IT regarding the development of an NGO Information Strategy develop an Information Model conduct a monitoring and reporting trial of an information model with NGO and MSD participants (linked to the Outcomes Framework Project) work with IT to define the requirements that relate to the potential information management solutions. Timing / Ongoing / Recommendations / Conclusions Recommend that milestone 1.13.1 be progressed via the milestones agreed for the Monitoring and Evaluation project which are: complete analysis of current MSD and NGO data collection systems by 30 October 2008 recommendations paper for 'Go Forward' options for data collection systems completed by 15 December 2008. Status = on track. |

### Changing Attitudes and Behaviour

| 2.1 KIA PUAWAI |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | All Taskforce members |
| Project Manager | Bede Hogan |
| First Programme of Action reference | Not in first Programme of Action |
| Objective and actions (as per Work Programme) Kia Puawai supported in its implementation by the Taskforce. Taskforce supports initiatives such as: increasing coverage of intensive home visiting providing free Early Childhood Education for all vulnerable children aged 18 months – 3 years developing an integrated identification, assessment and referral system for young children expanding Early Years hubs and teen parent co-ordinators initiatives key workers to support at-risk families expanding Social Workers in Schools. |
| Objective deadline | Ongoing |
| Purpose This cross-agency initiative is building an early years intervention system to help ensure all children flourish in early childhood and reach their potential as young adults capable of developing healthy, respectful and violence free relationships throughout their lives. |
| Key Milestones | Date | Description of Progress |
| 2.1.2 | Progress report delivered to Ministers on results of evaluations of pilot programmes to improve outcomes for children and their families. | Nov 08 | On track. Evaluations commenced. |
| 2.1.3 | B4School check pilot in place | Aug 08 | On track. Work underway. |
| Progress to date (previous 3 months work) Work has continued on evaluating four pilot programmes to improve outcomes for children and their families. This work will inform a report back to Cabinet on future funding decisions. Current ongoing work (next 3 months) The B4School pilot being progressed by the Ministry of Health will be in place by August 2008. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 2.2 IMPROVING ATTACHMENT |
| --- |
| Lead agency | Ministry of Health / Auckland District Health Board |
| Contributors | MSD, ACC, Education, NGOs |
| Project Manager | Pat Tuohy / Carol Stott |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) Promote and improve attachment between new-born babies and parents and care-givers. Actions include: progress a pilot see how well it works report draw on key findings from parent support and development programmes already focused on supporting attachment between young children and parents and caregivers. |
| Objective deadline | July 2009 |
| Purpose Supporting the promotion of healthy secure attachment in infants is important for the development of quality relationships between infants and parents and caregivers, and for its effect on human development and wellbeing. Promotion of secure attachment can be provided through provision of information to parents, and support with strategies that enhance attachment and address any parenting concerns. Early intervention is recommended for infants of high-risk carers if developmental or behavioural problems are detected. |
| Key Milestones | Date | Description of Progress |
| 2.2.1 | Inclusion of an additional visit in the Well Child Framework for first time parents, especially fathers and male partners | July 2009 | Not commenced |
| 2.2.2 | Promotion of infant-parent attachment and assessment of parent /child relationship difficulties in revised Well Child Framework | July 2009 | Not commenced |
| 2.2.3 | Training for Well Child Providers to promote secure infant- parent attachment | July 2009 | Not commenced |
| 2.2.4 | Establishment of a pilot in the Auckland District Health Board area to prevent Shaken Baby Syndrome (head injuries to babies caused by violent shaking). | TBC | Delayed. The Auckland DHB has decided not to proceed with this pilot as it was not considered a funding priority. The reason being is that the majority of babies admitted to Starship Hospital with head injuries as a result of Shaken Baby Syndrome are from outside the Auckland DHB’s area. The Ministry has been approached to fund a regional pilot across the three Auckland DHBs and is currently considering whether funding could be made available for this initiative. |
| Alert: Not commenced as initial scoping highlighted issues with the pilot site. A new approach is currently being considered by Ministry of Health. |

| 2.3 CONDUCT DISORDER / SEVERE ANTI-SOCIAL BEHAVIOUR |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | Education, Health, Justice, NGOs, OCC |
| Project Manager | Saskia Patton |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) Ensure comprehensive behavioural interventions for children aged 3 – 8 years with conduct problems and their families are delivered in accordance with the Inter-agency Plan by building on the specialist behaviours services already provided by the Ministry of Education. In addition, there will be the transitioning of existing services to older children and young people to evidence-based, best-practice interventions. The Taskforce supports the four action areas in the Inter-Agency Plan: leadership, co-ordination, monitoring and evaluation transition existing service provision to evidence-based, best-practice interventions establish an intensive, comprehensive behavioural service for 3 -7 year olds build a shared infrastructure for the delivery of specialist behavioural services. |
| Objective deadline | 2012 |
| Purpose Developing and delivering a suite of services for the 5% of early childhood and primary (and intermediate) school aged children who have conduct problems will reduce the prevalence of young people with these problems. Without appropriate interventions, these children are more at risk of becoming perpetrators of violence. Over time these services are anticipated to result in a subsequent reduction in cases of family violence. |
| Key Milestones | Date | Description of Progress |
| 2.3.1 | Establish experts advisory group | Mid Nov 2007 | Completed |
| 2.3.2 | Best practice report completed | June 2008 | Draft completed |
| 2.3.3 | Agency service reviews/stocktake completed | Dec 2008 | On track |
| Background This is an inter-agency project which seeks to improve behavioural interventions for 0-17 year olds across service areas of the Ministries of Education, Health, Justice and Social Development (CYF). In particular, it will establish a comprehensive behavioural service for children aged 3-7 years and transition existing services to older children and young people to evidence-based, best-practice interventions. Progress to date (previous 3 months work) The Advisory Group for Conduct Problems (AGCP) had its first meeting on 14 November 2007 and has met six times in 2008. Members of the AGCP have finalised the best practice report which is due to be printed and released in August 2008. The AGCP are currently drafting a second report: Translating Evidence into Practice which is looking at programme selection for 3-8 year olds and a research design to best support the implementation of selected programme(s). The Maori expert advisory group (Te Roopu Kaitiaki) has also been established to provide comment on responsiveness of ‘generic’ services to Maori consider the parallel development of programmes based in Te Ao Maori. Current ongoing work (next 3 months) AGCP will continue drafting the Translating Evidence into Practice report. MSD will be developing an implementation plan to support the delivery of the Inter-agency Plan. Te Roopu Kaitiaki will be drafting a report reviewing the evidence base and research requirements in considering the development of parallel Te Ao Maori-based services. Timing / Ongoing / Recommendations / Conclusions Status = on track |

| 2.4 CURRICULUM DEVELOPMENT |
| --- |
| Lead agency | Ministry of Education |
| Contributors | MSD (MYD), Health, TPK, MPIA, OCC, NGOs |
| Project Manager | Sue van Daatselaar |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) Children and young people aged 5-18 years develop the knowledge and skills that they need to support good decision-making, to make healthy choices, and to seek help when they need it. Actions include: provide support to enable schools to develop their programmes within the New Zealand curriculum to suit the diverse learning needs of their community strengthen whole-school, strengths-based approaches that promote resilience and confidence in young people and those adults who support them seek opportunities to identify and respond to children who are affected by family violence. |
| Objective deadline | Ongoing |
| Purpose The purpose of education is to help children and young people reach their potential and develop the competencies they will need to live, learn, work and contribute as active members of their communities. Education contributes to the prevention and reduction of family violence in New Zealand communities by providing a safe environment that teaches and models skills to enable children and young people to manage their own well-being and to relate in healthy ways with others. It provides children and young people with the opportunity to learn skills they might not otherwise receive in the home environment. To experience the benefits of education, students must participate and be engaged with the education system. The Ministry of Education supports educators to identify students who are at risk as a result of experiencing, witnessing or engaging in family violence and to work with parents, families and whänau, and other agencies to ensure these students are appropriately supported. |
| Key Milestones | Date | Description of Progress |
| 2.4.1 | Provide support to enable schools to develop their programmes within the New Zealand curriculum (NZC) to suit the diverse learning needs of their community. Release final curriculum and supporting resources for schools to support the implementation of the curriculum Professional leaders are supported to lead curriculum development, establish the conditions for professional learning and involve families/whanau in focusing on student achievement and educational outcomes based on the NZC. | Ongoing Ongoing | Ongoing. We have released the New Zealand Curriculum (English medium schools) and are continuing work to finalise Te Marautanga o Aotearoa (Māori Medium curriculum), which is planned for release in late 2008. We are continuing to work with principals, teachers and other stakeholders to support the implementation of these curriculum frameworks. Consultation on the position paper “Kiwi Leadership for Principals” has been completed and the document is being finalised. |
| 2.4.2 | Strengthen the implementation of whole-school, strengths-based approaches that promote resilience and confidence in children and young people and those adults who support them. Support up to 730 teachers per year in developing effective teaching and leadership skills to support the implementation of school-wide approaches to student well being / mental health. This involves strengthening teachers’ understanding of the connections between school organisation, curriculum design and delivery and community consultation and partnerships. Identify successful professional learning approaches for teachers from the evaluation of the student wellbeing contracts and incorporate in the design and delivery of ongoing professional development contracts. | Ongoing | Contracts providing support for up to 730 teachers per year in implementing school-wide approaches to student wellbeing and mental health are in place. The Ministry, the national coordinator and facilitators are continuing to review and improve the models used in the delivery of the Student Well-Being and Mental Health contracts and to integrate the learning in ongoing professional development contracts. |
| 2.4.3 | Seek opportunities to identify and respond to children and young people who are affected by family violence. Review the quality and accessibility of support available to educators who are concerned about children and young people affected by family violence. Develop a review of the support received by children and young people identified while at school as affected by family violence (in conjunction with obj 1.4 Child Maltreatment). | Ongoing Ongoing | The review has to-date focused on education support for children and young people in care. A draft education profile and plan guidelines and template is being trialled in early childhood services and primary and intermediate schools during 2008/09. A broader action plan has been delayed as it will be informed by the findings of a wider review of the contribution that education makes to the prevention of child maltreatment. This has been scoped as part of the work programme for Objective 1.4. A detailed project plan to the implement the review will be developed once it has been signed off by the Taskforce in August 2008. |
| Background In 2002, the Ministry of Education’s Curriculum Stocktake Report identified that, while many students were achieving at world-class levels, there are wide disparities in outcomes for diverse students. Progress to date (previous 3 months work) 2.4.1 The New Zealand Curriculum We have delivered presentations and workshops to groups of principals, teachers and other stakeholders about the direction and implementation of the New Zealand Curriculum (English medium curriculum). The second report on the exploratory studies of “early adopters” has been received. The document for Te Marautanga o Aotearoa (Mäori Medium curriculum) will be finalised and released in late 2008. Feedback has been received on the draft position paper, Kiwi Leadership for Principals. The feedback supported principals’ desire to be educational leaders, but emphasised the reactive nature of their role, and the need for greater support and development opportunities. This feedback has been incorporated into the final document to be released in August 2008. 2.4.2 Whole-school, strengths-based approaches that promote resilience and confidence in children and young people The Ministry, the national coordinator and facilitators are continuing to review the models used in the delivery of the Student Well-Being and Mental Health contracts. 2.4.3 Identifying and referring children affected by family violence to appropriate services The draft education profile and plan guidelines and template for children in care is currently being trialled in early childhood services and primary and intermediate schools in the Auckland District Health Board region over 2008/09. The scope of a review of the education sector’s contribution to child maltreatment prevention has been drafted and is awaiting sign-off from the Taskforce. The review is part of an inter-agency action plan that considers the effectiveness of the current sector systems, programmes and services in preventing child maltreatment (see Objective 1.4). Current ongoing work (next 3 months) 2.4.1 The New Zealand Curriculum Lessons will be drawn from the exploratory studies and monitoring and evaluating contracts to further develop the implementation strategy for the New Zealand Curriculum (English medium curriculum). The numbers of supported curriculum clusters will be increased as will the staff supporting the curriculum in the School Support Services. Consultation with schools, whānau, hapū, iwi and community groups is helping to scope the development of appropriate resources needed to implement Te Marautanga o Aotearoa (Māori medium curriculum) following its release. This work will continue through until 2010. A draft of the Professional Leadership Strategy is planned to be released in August 2008. 2.4.2 Whole-school, strengths-based approaches that promote resilience and confidence in children and young people Evidence from the Teacher Professional Learning and Best Evidence Synthesis Iteration are being used to strengthen the focus on improving outcomes for students and their families. More robust forms of data gathering are being developed to assess the impact of these changes. 2.4.3 Identifying and referring children affected by family violence Further trials of the education profile and plan will be implemented in other District Health Board regions throughout the country. The trials will enable the Ministry of Health, Ministry of Education and Child Youth and Family to test the suitability, content, and format of the education profile template. The trials will also inform cross-agency processes, and determine the effectiveness of the information collected. A detailed project plan to implement the review of the education sector’s contribution to child maltreatment prevention will be developed following the Taskforce’s approval of the scope of the review in August 2008. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 2.5 VIOLENCE IN THE MEDIA |
| --- |
| Lead agency | Families Commission |
| Contributors | NGOs |
| Project Manager | Radha Balakrishnan |
| First Programme of Action reference | Action 23 |
| Objective and actions (as per Work Programme) Create awareness of impact of violence in the media on children aged between 6 to 11 years. Actions include: scope an evidence-based public education and awareness programme aimed at parents scope financial implications develop an implementation plan. |
| Objective deadline | February 2009 |
| Purpose To scope a public education and awareness programme around violence in the media (its risks and impact) with an initial focus on parents of 6-11 year olds. |
| Key Milestones | Date | Description of Progress |
| 2.5.1 | Convene Advisory Group | Aug 2008 | On track |
| 2.5.2 | Develop plan | Oct 2008 | Not commenced |
| 2.5.3 | Draft Report circulated for comment | Dec 2008 | Not commenced |
| 2.5.4 | Report to the Taskforce | Feb 2009 | Not commenced |
| Background Violence in the media and its impact on society generally was raised at the meeting with the Family Violence Ministerial Team and with members of the Multi-Party Working Group on Family Violence, when the Taskforce’s First Report was presented in mid 2007. The first programme of action included an action to review how violence is portrayed in the media and in particular the 2004 Report on TV Violence in New Zealand, and advise on implications for the next Programme of Action. The Families Commission agreed to lead this work. The Taskforce supported raising awareness of the impact of violence within the media on children and young people. The 2004 report identified middle childhood (between 6-11 years) as a vulnerable group and it was agreed that this group should be the initial focus of any public education work. Progress to date (previous 3 months work) There have not been any major developments on this project in the last couple of months. The Broadcasting Standards Authority has recently released a report - Seen and Heard: Children’s Media Use, Exposure, and Response and reports the findings of a qualitative study of children’s use of electronic media, and the way parents and children mediate that use. The research involved interviewing more than 600 children aged between six and 13 and their primary caregivers. The focus of the research was how New Zealand children use and respond to television, radio, the internet, and cellphones. Work is underway to consider the implications of the research for this action. Current ongoing work (next 3 months) An advisory group will be convened and options will be developed. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 2.6 CAMPAIGN FOR ACTION ON FAMILY VIOLENCE |
| --- |
| Lead agency | Families Commission / MSD |
| Contributors | NGOs |
| Project Manager | Nick Farland / Gael Surgenor |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) Continue the Campaign for Action on Family Violence through: an advertising campaign resource development and distribution Community Action Fund projects. |
| Objective deadline | 30 June 2008 (ongoing to 2010) |
| Purpose This is a community-based social marketing campaign which aims to influence the behaviour of target audiences, including perpetrators of family violence and their influencers. The programme is based on research into attitudes and towards family violence and motivators and barriers to behaviour change. |
| Key Milestones | Date | Description of Progress |
| 2.6.1 | Run a television advertising campaign addressing attitudes to family violence and intimate partners violence during 2007/08 | 30 June 2008 | Completed to 30 June. The first set of television adverts was aired from September to January. The second set of four advertisements, focusing on stories of positive change went to air 17 February and ran to the end of March. Three additional weeks of advertising went to air early May, late May, mid-June and early July. |
| 2.6.2 | Develop a range of resources to support the messages of the television campaign during 2007/08 | 30 June 2008 | Completed. We have distributed over 30,000 copies of the Men’s Booklet, and 35,000 of the Children’s Booklet, both of which were first produced in February. Over 79,000 of the “Are you OK?” Booklet have been distributed since the beginning of the Campaign in September 2007. |
| 2.6.3 | Support local projects to support change at a local level by administering at least one round of the Community Action Fund. | 15 June 2008 | Completed. A total of 62 community initiatives have been funded in the first two rounds of the Community Action Fund. The campaign’s media advocacy work is proving highly effective. Community agency spokespeople are more visible in the media, and local coverage of national family violence issues has increased. |
| 2.6.4 | Measure the level of public awareness of the key messages of the Changing Attitudes and Behaviours Campaign | 30 June 2008 | Completed to 30 June. CSRE has released two sets of reach and retention survey results on the effectiveness of the Family Violence It’s not OK campaign. Both results show that the campaign has been extremely effective to date with 89% of those surveyed recalling the advertisements. |
| 2.6.5 | Administering two further rounds of the Community Action Fund to support local projects to support change at a local level. Mid 2008 and early 2009. | August 2008 Early 2009 | A third and fourth round have been agreed, for June 2008 and early 2009. Applications for round three closed on 10 June. Successful applicants will be announced by the end of July. Media advocacy work is also continuing. |
| 2.6.6 | Continue to support the messages of the television campaign during 2008/09 using the website, the 0800 information line and print resources. | Mid 2009 | The 0800 telephone line continues to provide information and support to an average of 665 callers per month. There has been an increase in the number of visitors to the campaign website, from around 4,000 per month over the first 3-4 months, and building steadily to over 8,000 visits per month for the last few months of the 2008/2009 year. |
| Background The Campaign for Action on Family Violence (the campaign) is a four year campaign that calls on everyone to help put an end to family violence in New Zealand. The national campaign was launched with TV advertisements in September 2007. The campaign message “Family violence – It’s not OK” has struck a chord with New Zealanders and has quickly become part of the kiwi vernacular. The campaign is supported by a website, an 0800 Information Line and a Community Action Fund that provides financial support for community-led activities. Progress to date (previous 3 months work) Resources (the booklets, Community Action Tool Kit, Resources for journalists and web-based information and support) continue to be distributed. The 0800 telephone line continues to provide information and support. The number of male callers to the line averages just over 40%. The campaign’s media advocacy work is continuing. Community agency spokespeople are visible in the media and local coverage of national family violence issues has increased. Advertisements from the first and second phase of the campaign have been screening at various times in May. A third and fourth round of the Community Action Fund have been agreed, with round three open currently, and closing on 10 June. A series of Community Action Fund regional hui took place to bring together recipients to share ideas and plan ahead. Current ongoing work (next 3 months) Additional weeks of the phase two advertisements going to air have been booked for mid-June, July and various times throughout 2008 and early 2009. Successful applicants for the third round of the Community Action Fund will be announced by the end of July. A third survey into the reach and retention of the TV advertisements will be conducted in September 2008 A nationwide face to face survey has begun that will specifically explore attitudes about violence towards women, inter-partner violence, and child abuse. A community study is underway that will provide an in-depth analysis of the impact of the campaign. Timing / Ongoing / Recommendations / Conclusions Status = all milestones to 30 June 2008 complete. Ongoing milestones on track. |

| 2.7 FAMILY VIOLENCE DEATH REVIEW PROJECT |
| --- |
| Lead agency | Ministry of Health |
| Contributors | MSD, Justice, Police, NGOs |
| Project Manager | Tanith Robb |
| First Programme of Action reference | Action 42 |
| Objective and actions (as per Work Programme) To establish the Family Violence Death Review Committee |
| Objective deadline | 31 June 2008 |
| Purpose The Family Violence Death Review Committee is being established to understand why family violence deaths occur and to enable changes to systems and practices that may contribute to the prevention of future deaths. |
| Key Milestones | Date | Description of Progress |
| 2.7.1 | Undertake consultation on draft Terms of Reference | 29 Feb 2008 | Completed |
| 2.7.2 | Finalise Terms of Reference and seek Ministerial sign-off | 31 Mar 2008 | Completed |
| 2.7.3 | Seek nominations for the inaugural members of the Committee | 31 Mar 2008 | Completed |
| 2.7.4 | Undertake Cabinet appointments process | 20 June 2008 | Delayed –Cabinet Appointments and Honours Committee is expected to consider the proposed appointees to the Committee on 23 July |
| 2.7.5 | Appoint members to the Committee | 31 June 2008 | Delayed – as above |
| 2.7.6 | Establish Committee | 31 June 2008 | Completed (Committee formally established, members not yet determined). |
| 2.7.7 | Induction and first meeting of the Committee | By 30 Oct 2008 | On track |
| Background The Ministry of Health has established a cross-agency Family Violence Death Review Project in close collaboration with the MSD, the MoJ, the Police and other key government and non-government organisations. The MoH reported to the Taskforce on 30 June 2007 and recommended that a formal mechanism for an interagency, multidisciplinary family violence-related death review system be established under the New Zealand Public Health and Disability Act 2000 (the NZPHD Act). The family violence death review system proposed involves the establishment of a ministerial committee that is parallel to, but separate from, the current mortality review committees mandated under the NZPHD Act. The Taskforce agreed to the recommendations in the report. An implementation manager was appointed in December 2007 to progress the establishment of the Family Violence Death Review Committee (FVDRC). On 13 February 2008, the Government considered a paper from the Minister of Health and noted that the Minister intends to establish a FVDRC under the NZPHD Act. On 20 February 2008, the draft Terms of Reference for the FVDRC were released for external consultation. Progress to date (previous 3 months work) In March, the Minister of Health approved the finalised Terms of Reference. A Senior Analyst (Legal) and a Senior Business Analyst were appointed in April to work on specific implementation issues, such as the FVDRC’s information requirements and death review process issues. In April, the MoH issued a call for nominations for the inaugural members of the Family Violence Death Review Committee. Nominations closed on 1 May, and 59 applications were received. Hon David Cunliffe referred the nominations to Hon Steve Chadwick for consideration. The FVDR Implementation Advisory Group had a meeting in May to discuss implementation issues associated with the establishment of the FVDRC. The FVDRC was formally established on 9 June 2008, however members are yet to be confirmed. Current ongoing work (next 3 months) An appointments paper has been drafted for Minister Chadwick and the Cabinet Appointments and Honours Committee is expected to consider the paper on 23 July 2008. The MoH will organise an induction day for new members of the FVDRC (Sept/October). The FVDRC will hold its first meeting (Sept/October). Timing / Ongoing / Recommendations / Conclusions Status = Complete as the Family Violence Death Review Committee has been formally established. The appointments process has been delayed; this process is now likely to be completed in July/August 2008. |

### Ensuring Safety and Accountability

| 3.1 FAMILY VIOLENCE COURTS |
| --- |
| Lead agency | Judiciary / Ministry of Justice |
| Contributors | Police, NGOs |
| Taskforce Liaison | Justine Cornwall |
| Project Manager | Karyn McLean/Dominic Lepa |
| First Programme of Action reference | Action 56 |
| Objective and actions (as per Work Programme) Two new Family Violence Courts established. Actions include: project planning identification of locations stakeholder consultation implementation. |
| Objective deadline | A variation is being sought to extend this deadline to early 2009 |
| Purpose To ensure all parties are prepared ahead of the implementation to support new Family Violence Courts being established. |
| Key Milestones | Date | Description of Progress |
| 3.1.1 | Project planning for implementation and establishment of two new Family Violence Courts | June 2008 | There has been some delay to this action. A variation is being sought to extend the deadline to early 2009. High level project planning has been completed. The Chief District Court Judge has confirmed Palmerston North (September 2008) and Whangarei (date tbc) as the locations for the new Family Violence Courts. More detailed project planning is now underway. |
| 3.1.2 | Identification of locations | June 2008 | Completed. Confirmed as Palmerston North and Whangarei. |
| 3.1.3 | Stakeholder consultation | June 2008 | Consultation has been delayed to allow time to identify locations for the Family Violence Courts. A variation is being sought to amend the deadline for this action to early 2009. |
| 3.1.4 | Communications strategy | June 2008 | The Communications strategy has been delayed to allow time to identify locations for the Family Violence Courts. A variation is being sought to amend the deadline for this action to early 2009 |
| 3.1.5 | Implementation of two new Family Violence Courts | June 2008 | There has been some delay for this action. A variation is being sought to amend the deadline for this action to early 2009 to allow time to establish the Court in Whangarei. |
| Progress to date (previous 3 months work) The Chief District Court Judge has confirmed Palmerston North and Whangarei as the locations for the new Family Violence Courts. Palmerston North will be implemented in September 2008 and Whangarei to follow, likely to be early 2009 (date tbc). Current ongoing work (next 3 months) As this is a Judicial initiative, start dates are dependent on the Judiciary being in a position to implement the new Family Violence Courts. The Ministry will consult with the Judiciary on a variation to this action to amend the deadline to early 2009 to allow time to establish the Courts in Palmerston North and Whangarei. The Ministry of Justice is working closely with the Judiciary, court staff and key stakeholders (including Police Prosecutions, Community Probation and community agencies) at these locations to plan the implementation of the courts. The Ministry will also be ensuring that staff and key stakeholders who will be working in these Family Violence Courts will receive specialist training on the dynamics of domestic violence and the philosophy of Family Violence Courts prior to the courts being implemented. A communications strategy will be developed in preparation for the launch of the new courts, in consultation with the Chief District Court Judge and the Minister for Courts. Timing / Ongoing / Recommendations / Conclusions Status = Some delay with confirmation of locations. More detailed project planning is now underway. A variation is being sought to amend the deadline for this action to early 2009. |

| 3.2 PROTOCOLS FOR FAMILY VIOLENCE COURTS |
| --- |
| Lead agency | Judiciary / Ministry of Justice |
| Contributors | Police, NGOs. |
| Liaison | Justine Cornwall |
| Project Manager | Karyn McLean/Dominic Lepa |
| First Programme of Action reference | Action 57, 58 |
| Objective and actions (as per Work Programme) A national protocol for improving how Family Violence courts are established and run. Actions include: develop protocols stakeholder consultation implementation. |
| Objective deadline | August 2008 |
| Purpose The purpose of this protocol will be to: outline the requirements of key staff involved in Family Violence Courts outline key areas of best practice to ensure there is consistency across all Family Violence Courts. |
| Key Milestones | Date | Description of Progress |
| 3.2.1 | Development of Operating Guidelines to ensure consistency across all Family Violence Courts | 21 Dec 2007 | Completed. Yet to be released. |
| 3.2.2 | Consultation and communication of Operating Guidelines with key staff and stakeholders | 21 Dec 2007 | Completed. |
| 3.2.3 | Approval and distribution of Operating Guidelines across all Family Violence Courts | August 08 | The Guidelines went out for broader consultation on 21 April 2008. A delay to August 08 has been required to extend the consultation period and allow for the incorporation of feedback. Consultation was completed in May 2008. |
| 3.2.4 | Communications strategy | August 08 | A communications strategy is being developed to coincide with the distribution of the Guidelines. An amended completion date of August 08 has resulted due to the delay in finalising the Operating Guidelines. |
| Progress to date (previous 3 months work) National Operating Guidelines for Family Violence Courts have been developed. The Guidelines have been considered by the Family Violence Courts Judges and approved by the Chief District Court Judge. The Guidelines went out for broader consultation on 21 April 2008 to key staff and stakeholders. This included the Law Society, Department of Corrections, New Zealand Police, NGOs, and Taskforce members. Consultation was completed in May 2008. Current ongoing work (next 3 months) A draft version of the National Operating Guidelines is forming the basis for Family Violence Training, which will be delivered to staff and key stakeholders at all Family Violence Courts by July 2008. The aim of this training is to ensure the successful implementation of protocols in all Family Violence Courts. The training has been scheduled across all courts in two phases from 20 May to the end of July 2008. This training will also be scheduled for the two new Family Violence Courts prior to their implementation. The Guidelines will be finalised and approved in August 2008. Timing / Ongoing / Recommendations / Conclusions Status = There has been a delay in finalising and approving the Guidelines. An amended date of August 2008 has resulted. |

| 3.3 SOCIAL SERVICES SUPPORTING COURTS |
| --- |
| Lead agency | Ministry of Social Development / Ministry of Justice |
| Contributors | Police, MWA, NGOs, ACC |
| Project Manager | Bede Hogan / Justine Cornwall |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) A social services system modelled around family violence courts to support the courts by linking services to ensure victims and observers are kept safe, perpetrators are kept accountable and responsible, and families are assisted with their recovery needs. Actions include: introduction of Independent Victim Advocate / support person role in all Family Violence Courts introduce specialist enhanced case management staff in all Family Violence Courts referral and funding for non-mandated stopping violence programme providers for offenders. |
| Objective deadline | April 2009 |
| Purpose A social services system modelled around family violence courts to support the courts by linking services to ensure victims and observers are kept safe, perpetrators are kept accountable and responsible, and families are assisted with their recovery needs. |
| Key Milestones | Date | Description of Progress |
| 3.3.1 | Project plan with ongoing milestones and agency roles completed | April 2008 | Complete. MoJ and MSD meet regularly to monitor the progress of this project. |
| 3.3.2 | Scoping and developing Independent Victim Advocate (IVA). | July 2008 | Government announced funding for this role in February 2008. Scoping and development of the IVA role is underway. |
| 3.3.3 | Introduce specialist enhanced case management staff in all Family Violence Courts (FVCs) | April 2008 | There has been a delay in this work. This initiative was part of a Budget Bid in 08 proposing a number of measures to support FVCs. Funding for this initiative was unsuccessful. MoJ is currently assessing other funding streams to fund this initiative. This work is ongoing. |
| 3.3.4 | Referral and funding for non-mandated stopping violence programme providers for offenders | July 2008 | Government announced funding for this role in February 2008. MoJ to determine and establish internal funding streams and processes for this initiative. From 1 July 2008, processes have been put in place at each FVC to manage funding of non-mandated programmes. |
| 3.3.5 | Consultation with other agencies and non-government organisations on the development of the role of the independent victim advocate/support person. | August 2008 | On track. The Ministry of Justice has begun consulting internally and with Police. A workshop is planned in early August with NGOs and external agencies. |
| 3.3.6 | The advocate/support person role will be rolled out in FVCs. | From 1 April 2009. | On track |
| Background A variation to this objective was approved by the Chair of the Taskforce on 4 April 2008. The variation was sought because the previous deliverables and milestones did not align with the direction the Chief District Court Judge has set for the Family Violence Courts (FVCs). The Government has announced that it will move towards fully funding actions 1 and 3 of this objective from 2008/2009 (Introduction of Independent Victim Advocate/support person role in all FVCs, and referral and funding for non-mandated stopping violence programme providers for offenders). Progress to date (previous 3 months work) The Project Plan and Terms of Reference for this objective have been finalised and agreed. The Ministry of Justice has begun work on developing the role of an independent victim advocate / support person to provide support and assistance to victims of domestic violence in the FVCs in conjunction with the MSD. Current ongoing work (next 3 months) Ongoing work on developing the role of an independent victim advocate / support person in FVCs. Consultation with other agencies and non-government organisations will take place in August 2008. The Ministry of Justice has begun consulting internally and with Police. A workshop is planned in early August with NGOs and external agencies. The independent victim advocate / support person role will be rolled out in FVCs from 1 April 2009. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

### Effective Support Services

| 4.1 MAORI SERVICE WORKFORCE DEVELOPMENT |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | TPK, NGOs, Education |
| Project Manager | Ann Dysart |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) Maori Service Workforce Development. Actions include: 60 Maori trained to work with the Mauriora framework. |
| Objective deadline | June 2008. Now ongoing |
| Purpose This proposal will allow for continued investment in the training and support of practitioners who work with Maori whanau/communities where there is violence. |
| Key Milestones | Date | Description of Progress |
| 4.1.3 | Funding and support for trained practitioners working to prevent violence in Maori whanau and communities, including assisting Mauri Ora practitioners to meet annual licensing and supervision requirements; | June 08 | Complete. A range of training has been delivered including Supervision, Facilitation skills, train the trainers, Media, and project management. An analysis is underway of the needs of practitioners in this field. It is expected that some of the further identified training will be available early in December 2008. |
| 4.1.4 | Delivery of training (including Mauri Ora training) to a minimum of 60 practitioners in 2007/08. The trainees will be Maori Practitioners who are working in both Maori and non-Maori provider organisations; | June 08 | Complete. 71 practitioners have undertaken training across the country, the final modules will be completed in August and a graduation is currently planned for November. Training is underway for practitioners in Tamaki Makaurau, Manawatu, Taranaki and the Central plateau. Training is also underway in the South Island. |
| 4.1.5 | Contract in place for the development of supervision systems and the training of appropriate supervisors for the graduates of the programme. | Jan 08 | Complete. Contract in place. Development of supervision systems underway, appropriate people currently being selected for training. |
| Ongoing The Maori Reference Group meet at least every two months (4.1.1). The contract with Te Korowai Aroha in regularly reported on (4.1.2). Progress to date (previous 3 months work) All Mauri Ora training is well underway, numbers are currently higher than contracted and the courses are generating excellent feedback A range of DVD of key Maori leaders giving messages around the kaupapa of family violence is underway, the first has been completed. Demand for resources has been high so new resources are being developed. Facilitation training for practitioners working with groups has been completed. Current ongoing work (next 3 months) With funding now on a continuing basis the negotiations are underway for the next round of training. The Provider is currently working with Te Kaiawhina Ahumahi to progress the recognition of learning provided, it is envisaged that students will eventually be able to cross credit Mauri Ora Training to a Diploma of Social Work. Timing / Ongoing / Recommendations / Conclusions Status = First phase complete. This objective will now be ongoing. |

| 4.2 PACIFIC SERVICE WORKFORCE DEVELOPMENT |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | MPIA, NGOs, Education |
| Project Manager | Richard Joblin |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) Variation submitted. Pacific Service Workforce Development. Actions include: preparation of a project plan to guide workforce training and development in family violence services for Pacific families. |
| Objective deadline | July 2008 (Variation submitted) |
| Purpose This work plans to increase the quality and diversity of services working to eliminate family violence in the Pacific communities. This will include identifying the capacity and capability of this workforce and the avenues needed to further build and support Pacific People in working to stop family violence in Pacific Families. |
| Key Milestones | Date | Description of Progress |
| 4.2.1 | Project plan developed under Pathway to Partnership to address building provider workforce capability and capacity. This will include the development of the Pacific workforce. | July 2008 | This work is now incorporated under the Pathway to Partnership plan. The project plan has been completed, however there have been major changes to the timelines for this work. A variation has been submitted. |
| Background This work is now incorporated within the Pathway to Partnership (P2P) plan. Pacific service workforce development is incorporated under the work-stream to address providers’ ability to build workforce capability and capacity. Progress to date (previous 3 months work) On 12 February 2008, the Government announced an additional funding package for the P2P plan worth $446 million, to be phased in over the next four years. A steering group for the P2P plan has overseen the development of P2P over the last year. A representative from the PAG is on this steering group. Current ongoing work (next 3 months) The P2P workforce and provider development project plan is currently being clarified. A variation to this objective has been submitted. Timing / Ongoing / Recommendations / Conclusions Status = some delay. |

| 4.3 SERVICE DEMAND DATA |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | NGOs, Justice, Health, ACC, Police |
| Project Manager | Dorothy Adams |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) Monitor increases in demand for family violence services resulting from the Campaign to create sustainable responses to increased demand. Actions include: develop monitoring framework create a system response mechanism. |
| Objective deadline | October 2008 |
| Purpose To identify changes in service demand associated with the roll out of the Campaign for Action on Family Violence. |
| Key Milestones | Date | Description of Progress |
| 4.3.1 | Measure initial service impact after the launch of the mass media campaign. | October 2007 | Completed |
| 4.3.2 | Repeat quantitative measures as above. | June 2008 | Some delay. Original data sets requested but not yet received. |
| 4.3.3 | Triangulation of quantitative data from qualitative field work. | October 2008 | Not commenced |
| Background Monitoring systems were developed to measure the initial impact in service demand associated with the Campaign for Action on Family Violence. These monitoring systems included data from the 0800 number, CYF and Police. The quantitative measures included in these monitors will be repeated. Qualitative data collected from the NGO sector in selected communities will compliment the quantitative monitors providing data directly from the NGO sector. The qualitative data collection will focus on the contribution that the Campaign for Action on Family Violence has had on any change in service demand experienced by the NGO sector since the commencement of the Campaign. Progress to date (previous 3 months work) Original data sets have been requested. Current ongoing work (next 3 months) Available data will be analysed to provide an estimate of service demand since the commencement of the Campaign. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 4.4a TRAINING OUR STAFF NB: there are only some agencies for whom it is relevant to complete a training project plan. |
| --- |
| Lead agency | ACC |
| Contributors | All agencies |
| Project Manager |  |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) Taskforce agencies at the point of contact with communities are enabled to respond to victims, observers and perpetrators effectively and safely. Actions include: assess available training options develop training that meets organisational needs plan and implement. |
| Objective deadline | Refer to objective 1.5b |
| Purpose To ensure frontline ACC staff are equipped with the skills and tools to respond to victims, spectators or perpetrators of Family Violence whether they be staff, clients of ACC or members of the communities in which ACC staff belong. |
| Key Milestones | Date | Description of Progress |
| 4.4.1 | Frontline staff skills developed | 31 Oct 2008 | Continuing work underway to scope requirements, attended MSD training. Milestone revised as training did not meet the needs of the organisation. |
| 4.4.2 | Establishment of specialist family Violence support people | 31 July 2008 | Continued scoping of ACC requirements. Initial training did not meet requirements. In the interim, in conjunction with an external provider, ACC have developed a support framework for staff that may be experiencing family violence while further work is done to develop more suitable and appropriate resources. Milestone date has been revised. |
| 4.4.3 | Training plan developed for all staff | 31 Oct 2008 | Modular based training identified as best solution is in development. Milestone revised. |
| This objective relates directly to Objective 1.5b – Family Violence Free Workplaces (FVFW). Ongoing work Continuing work underway to scope FVFW training requirements, after attending MSD FVFW training. Continued scoping of ACC requirements. Initial training provider assesses did not meet requirements. Modular based training identified as best solution is in development. |

| 4.4b TRAINING OUR STAFF |
| --- |
| Lead agency | CYF |
| Contributors | All agencies |
| Project Manager | MSD contact – Sarah James/Gerard Boomfield |
| First Programme of Action reference | N/A |
| Objective and actions (as per Work Programme) Taskforce agencies at the point of contact with communities are enabled to respond to victims, observers and perpetrators effectively and safely. Actions include: assess available training options develop training that meets organisational needs plan and implement. |
| Objective deadline | Ongoing |
| Purpose To ensure that frontline social work staff are able to recognise and respond to the dynamics present in situations of family violence. |
| Key Milestones | Date | Description of Progress |
| 4.4.1 | Where identified as part of their professional development plan, frontline social work staff attend a Family Violence workshop. | As scheduled in training calendar | A workshop has been available for some time, this is being reviewed as part of an ongoing quality assurance process and will now be available as part of the specialists stream within the new Practice Induction programme. |
| 4.4.2 | Family Violence is discussed in numerous other parts of the new Practice Induction in the workplace learning modules, the classroom based two week Practice Foundation and various learning forums that are part of the new Practice Induction programme. | As scheduled in training calendar | Ongoing. |
| Ongoing work Where identified as part of their professional development plan, frontline social work staff attend a Family Violence workshop. This workshop has been available for some time, this is being reviewed as part of an ongoing quality assurance process and will now be available as part of the specialists stream within the new Practice Induction programme. Family Violence is discussed in numerous other parts of the new Practice Induction in the workplace learning modules, the classroom-based two week Practice Foundation and various learning forums that are part of the new Practice Induction programme. |

# First Programme of Action update

Summary Analysis

The Taskforce for Action on Violence within Families’ (the Taskforce) first programme of action initially consisted of 76 actions which were developed from the Taskforce’s First Report. This was consolidated to 53 actions.

Of these, 26 are complete. Work has commenced on another 18 actions and these are now either ongoing, business as usual, or are annual events. The remaining actions have been subsumed into the Ongoing Programme of Action and, along with other ongoing work, are now reported on and monitored through the regular Monitoring Reports provided to every Taskforce meeting.

Status

Complete = Action complete. May have informed development of work in Ongoing Programme of Action.

OPOA = Work in these actions has been incorporated into the Ongoing Programme of Action, refer to objective number.

Ongoing or Annual = Initial stage complete, currently Ongoing or business as usual. Some are Annual occurrences.

| # | Action | Agency | Information | OPOA # | Status |
| --- | --- | --- | --- | --- | --- |
| Leadership |
| 1 | Developing the next Programme of Action (POA) | All TF | OPOA released Feb 2008 | 1.1 | Complete |
| 3 | Successful implementation of POA | All TF | Incorporated into OPOA | 1.1 & 1.1a | Complete, ongoing reporting |
| 7 | Drawing on Maori and Pacific advisory groups | MSD | Representatives on TF, ongoing MRG and PAG meetings advise the TF. | Led to 1.2, 1.3, 1.6, 1.9, 1.10, 2.4, 4.1, 4.2 | OPOA |
| 8 | Incorporating migrant and refugee perspectives | MSD | Informed OPOA | 1.11 | OPOA |
| 9 | Aligning business planning to reflect Taskforce vision | Sec. | Next round of SOIs (2008/2009) to be monitored. | 1.1 | Annual Ongoing |
| 12 | Maintain overview of government strategies to ensure goals and activities are complementary with our work | All TF | Business as usual. Secretariat watching brief to ensure TF are aware of all relevant govt strategies. All TF agencies info share on new strategies, and maintain overview of relevant govt strategies. Also links to other actions. | 2.1 2.3 | Complete to date, Ongoing |
| 13 | Family Violence research strategy | FC | Initial report provided Oct 2007, gaps analysis and other areas where work needed. Discussion doc sent early 2008 on topic priority – ongoing work being done through 2008 in consultation with other research agendas. | Informs 1.9-1.12 Led to 1.13 NGO data | Ongoing |
| 14 | Monitoring the level of family violence in NZ | FC | Refer to Research Strategy | Led to 1.13 & 1.7 | Ongoing |
| 15 | Horizontal learning | MSD | Incorporated into OPOA, Ongoing | 1.7 | OPOA |
| 19 | Evaluate the first POA | MSD | Workshop April 2007. Remaining ongoing actions from POA will be monitored through regular Monitoring Reports. | 1.1a | Complete |
| 21 | Families Commission research programme | FC | 3 year research complete 21a Improving Family Violence surveillance data 21b Elder abuse and neglect research – released Feb 2008 | Informed OPOA | Complete |
| 22 | ACC research programme | ACC | 22a Sensitive claims 22b Effectiveness evaluation 22c Whanau Ora research - extended to mid 2008 22d Evidence based guidelines. |  | Complete 22c only is Ongoing |
| Changing attitudes and behaviour |
| 23 | Review violence in media | FC | Informed development of 2.5 | 2.5 | Complete |
| 29 | Using research to guide Campaign strategy | MSD | The Campaign continues to 2010, with further development being guided by research and evaluation | 2.6 | OPOA |
| 35 | Campaign strategy | MSD / FC | As above | 2.6 | OPOA |
| 36 | Mass media campaign | MSD / FC | Phase one started Sept 2007, Phase two started Feb 2008. Both phase adverts to be repeated in 2008 and early 2009. | 2.6 | OPOA |
| 37 | Nurturing leaders… | MSD | Business as usual. Identified (and funded) through the Community Action Fund. | 2.6 | OPOA |
| 38 | Partnerships with NGOs | MSD/ FC | NGO groups are contracted to be funded for local initiatives. | P2P | Ongoing |
| 39 | Community Action Fund | MSD | Round two complete, 62 initiatives funded in total. Successful applicants for third round announced end July 2008. | 2.6 | OPOA |
| 40 | Building knowledge – media advocacy etc | MSD/ FC | 40a media advocacy - FACS 40b FV awareness training – also led to 1.5 40c Toolkit re-released 40d White Ribbon day | 2.6 2.6 1.5 2.6 - | OPOA Ongoing Ongoing Complete Annual |
| 4142 | Family violence death reviews | MoH | Ministerial committee established in June 2008, appointments due to be made in July/August 2008. | 2.7 | OPOA |
| Ensuring Safety and Accountability |
| 43 | Sharing information in a way that promotes safety and wellbeing | MoJ | The Law Commission and the Privacy Commissioner are exploring approaches to the issue of government information sharing. The Law Commission will release a discussion document in the second half of 2008, with a follow up report in the first half of 2009. |  | Initial work complete, Ongoing |
| 44 | Family Violence victims know what support and services are available | MoJ | New comms material developed and distributed at end 2007/early 2008. Available on Family Court website. |  | Complete |
| 45 | Maximising safety factors when managing court rosters | MoJ | Security policy complete, and was sent to all courts as a circular on 1 April 2008. |  | Complete |
| 46 | Increased thresholds for legal aid eligibility | MoJ | Thresholds increased. Legal aid regulations in force from Mar 2007. |  | Complete |
| 47 | Begin a review of legal aid remuneration rates | LSA | Review complete. Changes recommended, likely to happen 2008. |  | Complete |
| 48 | Improving information courts provide about legal aid | MoJ | Info updated and provided in court info packs and in DV packs, Dec 2007. Court staff also provided with info for public enquiries. |  | Complete |
| 49 | Testing fixed fees for legal aid | MoJ | Testing complete. Recommendation from analysis of testing will go to Agency Board in 2008. |  | Complete |
| 50 | Building safe and effective programmes for couples and families | MSD / MoJ | Service specifications set. MoJ in consultation with NZ Assoc of Counsellors, timeframes to be set. |  | Ongoing |
| 51 | Build capacity of interpreters in Courts | MSD / MoJ | More interpreters available in courts. Business as usual to continue building availability. |  | Complete |
| 52 | Investigate introduction of advocates in courts | MWA / MoJ / MSD | Investigation done by MWA. MoJ and MSD are now developing an independent victim advocate role in 2008 for implementation in the eight Family Violence Courts in April 2009. | 3.3 | Complete |
| 53 | Enhanced ability for courts to contact victims directly | MoJ / Police | Already possible, MoJ and Police will continue improving standardised process for CSV1 compliance and referral. |  | Complete |
| 54 | Review purchasing plans for programmes | MoJ | 2008 tender round complete. |  | Complete |
| 55 | Improve process for prosecutions for non-attendance at programmes | MoJ / Police | Memorandum of understanding between MoJ and Police for the transfer of prosecutions to Police signed. Transfer completed in June 2008. |  | Complete |
| 56 | Establish four additional Family Violence Courts | Judiciary / MoJ | Four established. Two further to be established in 2008/early 2009 in Palmerston North and Whanagrei. | 3.1 | Complete |
| 57 | Family Violence Courts Evaluation | MoJ | Waitakere and Manukau evaluation complete. Report has been circulated to the Taskforce, due to be released. | 3.2 | Complete |
| 58 | Forum to identify best practice for information exchange | MoJ | Held March 2007. Best practice ideas generated informed development of guidelines by agencies. |  | Complete |
| 60 | Enforcement of protection orders (POs) – police training, performance measures and policies | Police | Initiatives on addressing family violence “big picture” (which include PO’s) complete. Ongoing work continuing. 60a Training 60b Performance measures 60c National investigation and prosecution policies. Protection Orders research response also monitors this work, next report due to Minister end August ‘08. | Many & 4.4 | Many initiatives complete, Ongoing work |
| 61 | Support and training for lawyers working in family violence-related areas | Judge Boshier | Workshops for FC lawyers done in 2007, Law Soc also produced a resource booklet. Similar training is likely to be ongoing. |  | Complete |
| 62 | Define options to improve information sharing between agencies and the Courts | MoJ | Much information sharing already possible (judges in particular). Further work on information sharing will be undertaken as part of MoJ’s ongoing policy work on domestic violence. | Part of 3.3 | First stage complete Ongoing 2008 & beyond |
| 63 | Simplify application forms for Protection orders | MoJ | Explanatory leaflet complete May 2008. Any changes to the form can only happen by regulation change, which will be explored following amendments to the DVA. |  | First stage complete, Ongoing 2008 & beyond |
| 64 | Improve the use of security resources available to courts | MoJ | The budget bid for new security resources and initiatives was unsuccessful. The Ministry continues to prioritise the use of its existing Court Security Officers, and other resources where necessary. |  | First stage complete, Ongoing 2008 & beyond |
| 65 | Consider an office to provide DVA-specific legal services | LSA MoJ | Currently developing objective and milestones as part of business planning. |  | Ongoing 2008 & beyond |
| 66 | Determine level of attendance and performance of perpetrators at programmes | MoJ | MoJ currently collating and analysing data that will illustrate how attendance at programmes by respondents are managed. Due to complete analysis an report to TF in Sept 2008. Result will be used to improve processes and reporting, and improve the management of attendance at programmes by respondents to protection orders. |  | Ongoing 2008 & beyond |
| 67 | Develop options to ensure perpetrators attend and complete programmes | MoJ | Further phase of Action 66. |  | Ongoing 2007/2008 & beyond |
| 68 | Information for perpetrators on programmes | Police | Information distributed |  | Complete |
| 70 | Ensure the range of programmes matches the profiles of perpetrators | Corrections / MoJ | Corrections have completed a comparative analysis of violence programmes in prison (including the violence components of generic programmes) with the DV programmes which offenders based in the community are referred to. Options to potentially address gaps in programmes for prisoners with DV-related offences formulated. Currently analysing these options. On track to meet the 30 June deadline. |  | Ongoing 2007/2008 & beyond |
| 71 | Local Case Collaboration (FVIARS) | CYF / Police | FVIARS phase one complete, second phase - nationwide roll-out underway by mid-2008. | Informs 3.3 | Phase one complete, Ongoing 2008 & beyond |
| Effective Support Services |
| 72 | Govt investing $9 million over the next four years | MSD | 2006/2007 contracts complete and funding took place. Continued funding of contracts as above, from baseline. |  | Dev. Complete Ongoing to 09/10 |
| 73 | Develop new funding model | MSD | Pathway to Partnership (P2P) developed and ongoing. $20.4 million allocated in 2007. $446 million announced 12 Feb 2008 to fund essential NGO child and family services. | 2.1 | Complete OPOA |
| 74 | Cost family violence and family support services | MSD | Costing tool developed as part of P2P as above. | 2.1 | Complete |
| 75 | Build on existing workforce and organisational development initiatives | MSD | P2P Funding announced on 12 Feb 2008 to build a sustainable NGO sector. Ongoing. | 2.1 | Dev. complete. Ongoing 2008 & beyond |
| 76 | Continue to promote the use of integrated contracts | MSD | Funding for Outcomes developed and implemented. These contracts now part of FACS core business under the Integrated Contracts team. |  | Complete |

# How this report works

The Ongoing Programme of Action Monitoring Report is organised into two sections:

- A summary section – which provides an overview of the key highlights over the previous two months, and identifies the hotspots that need to be monitored closely over the upcoming two months to ensure objectives remain on track.

- A monitoring report section – which includes two key parts:

  - A summary of the progress of each objective over the last three months and an overview of the work that is expected to occur over the next three months.

  - Summary information from the project plans for each objective.

The report format is new and still evolving. There are some objectives that require more ongoing information. The Secretariat will work to extend this information with each report.

We have tried to layer the information provided in the report so that Taskforce members can get a snapshot of where things are at and refer to the Monitoring Report section for more detail on each objective, its milestones, and the responsible project managers within each agency if they wish to follow work up or find out more information.

The Taskforce’s planning and reporting hierarchy consists of the following:

- objectives – specific work that has been signalled in the programme of action

- actions –  specific work signalled in the programme of action, as part of an objective and/or in the Taskforce’s work programme which sits beneath the programme of action

- key milestones – taken from individual agency project plans.

We have also introduced a formal variation process, which aims to:

- maintain the integrity of the Taskforce’s programme of action

- ensure there is transparent communication within the Taskforce about changes to objectives and/or actions

- ensure the objective and actions remain relevant to the Taskforce and its priorities.

The variation process involves:

- completing the attached variation template

- consulting with appropriate Taskforce agencies over the changes to gain agreement and buy-in (this will be left to the responsible Taskforce agency seeking a variation to determine)

- sending a draft of the variation to the Secretariat to review before it is finalised, the Secretariat will then provide feedback and the variation can be finalised

- getting the responsible Taskforce member to sign the variation (thereby finalising the variation)

- sending the finalised variation to the Secretariat

- the Secretariat will brief the Taskforce Chair and seek his sign-off

- the Secretariat advise the agency seeking a variation of the outcome

- the outcome is noted in the Taskforce monitoring report.

A formal variation is required when a Taskforce agency wants to change an objective, action or both.  Formal variations are not required to change milestones, however, any milestone changes must be provided to the Secretariat so that a log can be kept and changes can be tracked over time. Formal variations are not required for milestones because milestone changes should not compromise an objective and its associated actions.

A formal variation needs to be completed if the deadline for completion of an objective and associated actions changes. This is because the overall objective and actions are compromised.

The variation template is attached to this report, an electronic copy of which can be obtained from the Taskforce Secretariat.

Reporting frequency

Ongoing Programme of Action Monitoring Reports will be produced for each Taskforce meeting. If a Taskforce meeting is changed to a workshop then a report will still be produced but will be circulated in hard copy only.

Other information

The information in the monitoring report centres on the key milestone information provided by each Taskforce agency.

To ensure the monitoring report remains current, as each milestone is reported complete it will be dropped from the report. The Secretariat will keep a record of all milestones so that this information can be used at a later date, if necessary.

| To | Peter Hughes | Date |  |
| --- | --- | --- | --- |
| From |  |
| Security Level | In Confidence |
| request to amend Work Programme Objective or Action |
| Action | For your approval |

I am seeking your approval to change an objective or action from the work programme for the Taskforce for Action on Violence within Families.

Current Deliverable:

[Insert Project / Work Programme Objective and/or Action]

[Insert current milestone/s (from project plan template)]

Changed to:

[Insert Project / Work Programme Objective and/or Action]

[Insert new milestone/s (also complete new project plan template)]

Reasons for a Variation Request

A variation to this deliverable has become necessary as:

- [please insert reason/s for variation]

Consultation

In seeking a variation to this deliverable, I have consulted with the following people:

| Name | Position and organisation |
| --- | --- |

Impact

The impacts in agreeing to this change are:

- [add details of any impact such as reporting to Cabinet, other key project timeframes, budget initiatives, reputation, legislation.]

The impacts in not agreeing to this change are:

- [add details of any impact such as reporting to Cabinet, other key project timeframes, budget initiatives, reputation, legislation.]

Recommendation

It is recommended that you:

- agree to a variation to an objective or action found in the Taskforce’s work programme

[Insert Project / Work Programme Objective and/or Action]

[Insert new milestone/s (also complete new project template)]

Approve / Decline

| Xxxxx (Taskforce representative) |  |  |
| --- | --- | --- |
| XXXXX (Taskforce agency) |  | Date |

| Peter Hughes |  |  |
| --- | --- | --- |
| Chair |  | Date |
| Approved ( Not Approved ( |

# Footnotes

While the Inter-agency Plan references to establish an intensive, comprehensive behavioural service for 3 -7 year olds, the ongoing work programme now discusses delivery to 3-8 year olds.