| Inspiring behaviour change and empowering families/whānau to respond |
| --- |
| Key Milestones complete Supporting E Tü with positive messaging Work with Pacific Advisory Group (PAG) to foster Pacific leadership | Date 1 June | [List here milestone completed from last report] Mana Manaaki advertisements and messaging in Mana and Tü Mai June/July editions Pacific Champions of Change Fono on Stopping Violence held in Auckland |

Work Underway

| Deliverable | Lead Agency | Date due | Milestones | Status | Comments |
| --- | --- | --- | --- | --- | --- |
| Summary reports outlining activity will be provided for each Taskforce meeting | MSD | 8 Sept 10 Nov | Written report provided to the Taskforce for meetings on 29 Sept and 1 Dec |  |  |
| Develop and air ads for a third phase of “It’s not OK” campaign, focussed on giving and receiving help | MSD | April 2010 27 July 31 Aug | Concept reported to Taskforce meeting 28 April Report on Giving, Receiving and Seeking Help published on MSD website TV ads presented to Ministerial Group Third phase advertising campaign launched |  | Two 45 second adverts have been filmed and are currently being re-tested with the same group of audiences. They are scheduled to go to air on 22 August |
| Develop resources, communications and social marketing strategies that support attitude and behaviour change | MSD | 30 Sept | New website material that supports people to give help and influence friends and family |  | Resources include: booklets, media articles, website resources and 0800 info line that support people to give help and influence friends and family |
| Work at community level to support local solutions and help share successes | MSD | 31 Aug | Distribute case studies of successful community initiatives |  | An example of this is Taiohi Morehu rangatahi leadership project in Hutt Valley |
| Supporting E Tü with positive messaging | MSD | I Aug | Korero/Awai advertisements and messaging in Mana and Tü Mai Aug/Sept editions |  | Ads placed in Mana and Tu Mai in June/July issues, two-monthly cycle of themes using different media including Maori radio and health TV throughout the year |
| Work with Pacific Advisory Group (PAG) to foster Pacific leadership | MSD | April – May 2010 24-25 June 8 Sept | PAG community fono in nine different locations National Summit: Pacific Champions of Change Fono on Stopping Violence held in Auckland Report on the Fono for the 29 Sept Taskforce meeting |  | West, South and Central Auckland, Hamilton, Hastings, Palmerston North, Wellington, Christchurch, Dunedin |

| Supporting and encouraging leadership locally |
| --- |
| Key Milestones complete | Date | [List here milestone completed from last report] |

Work Underway

We cannot determine milestones for all the work in this objective as we will be working with communities to support their initiatives. We will provide summary reports about these initiatives when appropriate.

| Deliverable | Lead Agency | Date due | Milestones | Status | Comments |
| --- | --- | --- | --- | --- | --- |
| Summary reports outlining activity will be provided for each Taskforce meeting | MSD | 8 Sept 10 Nov | Written report provided to the Taskforce for 29 Sept and 1 Dec meetings |  |  |
| Form partnerships with local authorities that support mayors, their councils and community organisations | MSD | 2July July | Waihi community campaign launched Collaboration in Taranaki involving council, family violence networks, DHB, Chamber of Commerce and sports clubs |  | Currently also working with Waitakere, Manukau, Taupo, Whangarei, Rotorua, Christchurch and Hamilton councils |
| Work with journalists and journalism schools | MSD | 30 Aug Dec | Training seminar delivered to one journalism training school Training at 7 journalism schools completed |  | Seminars in journalism schools start in August. The Dominion Post has asked for training for all staff |
| Develop community action tools and disseminate information about what works to prevent family violence | MSD | 30 Aug | New community action toolkit launched |  | Community action toolkit launch, Maori Reference Group updating Maori Leadership toolkit |

| Support to improve family violence responses in each community, including developing and trialling an integrated, community-based family violence response model |
| --- |
| Key Milestones complete | Date | [List here milestone completed from last report] |

Work Underway

| Deliverable | Lead Agency | Date due | Milestones | Status | Comments |
| --- | --- | --- | --- | --- | --- |
| Back communities to make good decisions about local family violence responses | MSD | May ongoing | Develop new workshops for communities focussed on family violence prevention and coordinated community action Deliver the workshops to community groups |  | The new workshop ‘Mobilising Communities for Change’ has been developed and delivered in Auckland, Christchurch and Palmerton North. The workshops will be delivered to other communities around the country and will be available in the new ‘Creating Change’ toolkit being produced by the Campaign. |
| Develop and trial an integrated community-based family violence case response model | MSD / Police / NCIWR | 11 August 10 Sept 12 Oct 2 Nov 9 Nov 1 Dec | Update to Taskforce - ToR, key messages Written update to Taskforce for 29 September meeting Options established Briefing and draft recommendations to Family Violence Ministerial Group for 17 November meeting Final recommendations to Chair of Taskforce Presentation to Taskforce |  |  |

| Better integration of justice and social service responses |
| --- |
| Key Milestones complete | Date | [List here milestone completed from last report] |

Work Underway

| Deliverable | Lead Agency | Date due | Milestones | Status | Comments |
| --- | --- | --- | --- | --- | --- |
| Review the delivery of MoJ-funded domestic violence programmes…,and investigate a broader set of responses | MoJ | 28 July 3 Nov | Scoping meeting with Taskforce members and Judge Boshier on the differential response model Initial advice to Chair of Family Violence Ministerial Group |  | Initial scoping work underway to agree work to be completed |
| Implement and evaluate Community Link in Courts (CLiC) initiative in Porirua | MSD / MoJ | 31 May Apr 2011 | Implemented in Porirua Family Violence Court Evaluation report on the implementation of CLiC |  | Quarterly monitoring reports of initial take-up data available to the DCE steering group in the interim. |

| An ongoing evaluation approach and measuring results |
| --- |
| Key Milestones complete Māori Research Agenda | June 2010 | [List here milestone completed from last report] Suite of family violence documents published on website http://www.tpk.govt.nz/en/in-print/our-publications/fact-sheets/safer-whanau/?q=violence |
| Deliverable | Lead Agency | Date due | Milestones | Status | Comments |
| Research to better understand family violence and successful intervention models for: |  |  |  |  |  |
| i. Whānau Māori | TPK | Nov 2010 | Identify gaps for future research priorities |  | TPK and MRG have agreed that the work underpinning the Maori Research Agenda is not robust enough to determine which priorities should be progressed and how. TPK is analysing current evidence to identify the gaps where future research should be done. |
| ii. Pacific communities | MPIA / MSD | Aug 2010 | Research priorities to be determined |  | MPIA and MSD currently consulting with PAG on research priorities |
| iii Refugee and new Migrant communities | MSD / MWA | 31 Aug 15 Oct 25 Nov | Preliminary report identifying selected community groups for case study and emergent themes Presentation of research findings Dissemination of case study findings |  | Stakeholder consultation underway |
| Results based accountability | MSD | 1 Jul | Introduced results based accountability reporting in the provider return reports for a number of FACS funded services covering three questions: how much did we do? how well did we do it? and is anyone better off? |  | The FACS funded family violence related services that now have results based accountability reporting are; Te Rito, Family Violence Education, Child Advocates, and Elder Abuse and Neglect Prevention |
| Monitoring the impact of new legislation | Police MoJ | 27 Oct 10 Nov 10 Nov | Update to Ministerial group meeting on 17 Nov on Police Safety Orders issued and breached from 1 July On-going six monthly reports to the Taskforce on Police Safety Orders issued and breached, due for Taskforce meeting on 1 Dec Report on Protection Orders issued by the criminal courts since 1 July for Taskforce meeting on 1 Dec |  |  |
| Dashboard of Indicators | MSD | Sept 2010 Apr 2011 18 May 2011 | Convene sub-group to investigate whether any new data is available for inclusion Put Dashboard on Taskforce pages of the MSD website Request updated data Dashboard updated with new data and sent to the Taskforce for 1 June meeting |  |  |

| Objectives from 2007 Ongoing Programme of Action including E Tu Whanau-ora and Programme of Action for Pacific Peoples |
| --- |
| Key Milestones complete | Date | [List here milestone completed from last report] |

Work Underway

| Deliverable | Lead Agency | Date due | Milestones | Status | Comments |
| --- | --- | --- | --- | --- | --- |
| 1.2 Māori Programme of Action E Tu Whānau-ora | MSD MRG | 19 Jan 2011 | Annual report on activity provided to the Taskforce for the 2 February planning day |  |  |
| 1.3 Pacific Programme of Action | MSD PAG | 19 Jan 2011 | Annual report on activity provided to the Taskforce for the 2 February Planning day |  |  |
| 1.4 Child Maltreatment | MSD |  | Updates to be provided as appropriate to the Taskforce on work across agencies to prevent child maltreatment |  |  |
| 1.5 Family Violence Free Workplaces | MSD ACC NZPolice | Dec 2010 June 2011 | Assess and evaluate agency programmes Complete a blueprint/model for implementing FVFW in workplaces |  |  |
| 1.6 Iwi-led Crime Prevention | Police | 1 Dec | Annual report on family violence-related activity provided to the Taskforce |  |  |
| 1.7 Family Violence Clearinghouse | MSD | Sept 2010 | Negotiate new contract |  |  |
| 1.12 Elder Abuse | MSD | 8 Sept 29 Sept | Progress report on preventing and responding to elder abuse and neglect for Taskforce meeting on 29 Sept Report to Minister for Senior Citizens on proposed next steps in preventing and responding to elder abuse and neglect |  |  |
| Curriculum development | MoE | 8 Sept | Work to promote resilience and confidence in young people, and to support students affected by family violence is ongoing. The Ministry of Education will provide periodic reports to the Taskforce on activity in this area. The first report will be available for the Taskforce’s 29 September meeting. (tbc with MoE) |  |  |