Ongoing Programme of Action

Monitoring Report

March 2010

Prepared by the Secretariat for the Taskforce for Action on Violence within Families

Contact: Kathy Puketapu

Ph: 04 916 3550  |  Fax: 04 917 5583  |  Email: kathy.puketapu001@msd.govt.nz

# Contents

Contents	1

Summary	3

Highlights	3

Leadership	3

Changing Attitudes and Behaviour	3

Hotspots	4

Alerts	4

Variations	5

Monitoring Report	8

Milestone updates and three month summaries	9

Leadership	9

1.1  Facilitation of the Ongoing Programme of Action (OPOA)	9

1.2  Māori Programme of Action	10

1.3  Pacific Programme of Action	11

1.4  Child Maltreatment	13

1.5  Family Violence Free Workplaces	15

1.6  Iwi-Led Crime Prevention	17

1.7  Family Violence Clearinghouse	18

1.9  Māori Research Agenda	20

1.10  Pacific Research Agenda	21

1.11  New Migrant and Refugee Research Agenda	22

1.12  Elder Abuse	23

1.13  Data on NGO Service Delivery	24

Changing Attitudes and Behaviour	26

2.1  Kia Puāwai	26

2.2  Improving Attachment	26

2.3  Conduct Disorder / Severe Anti-Social Behaviour	27

2.4  Curriculum Development	29

2.5  Violence in the media	32

2.6  Campaign for Action on Family Violence	33

Ensuring Safety And Accountability	38

3.3  Social Services Supporting Courts	38

Effective Support Services	40

4.1  Māori Service Workforce Development	40

4.2  Pacific Service Workforce Development	40

First Programme of Action update	42

How this report works	48

Variation: Request to amend work programme objective………………………………………51

# Summary

The Taskforce for Action on Violence within Families (the Taskforce) first programme of action initially consisted of 76 actions, which were later consolidated to 53 actions. A progress summary on these 53 actions is provided towards the end of this report.

The Taskforce’s Ongoing Programme of Action (OPOA) originally consisted of 31 objectives which form the Taskforce’s work programme. Of the original 31 objectives, 21 remain. To meet each objective, actions and milestones have been identified. This report provides a progress report against the objectives, actions and milestones.

For more information on this report, how it is organised and the formal variation process, please refer to the “How this report works” section at the end of the document.

Objective status

| On track | 11 |
| --- | --- |
| Project re-scoped or minor delay | 1 |
| Alerts | 8 |
| Variations | 1 |
| Total number of objectives remaining | 21 |

Many of the objectives have been completed or have not proceeded where the initiative has changed.  These are included in Table 1a.  The Taskforce is developing a new annual programme and this will eventually replace this report once finalised.

## Highlights

This section provides an overview of key Taskforce initiatives for the reporting period December 2009 to March 2010.

### Leadership

### Child and Family Protection Bill

The Child and Family Protection Bill had its first reading in the House on 11 February 2010 and has been referred to Justice and Electoral Committee.  The Committee is due to report back to the House on 11 August 2010.

### Changing Attitudes and Behaviour

### Campaign for Action on Family Violence

The resource Aroha in Action has had huge uptake around the country.  Amokura Family Violence Prevention Consortium, SKIP and the Campaign for Action on Family Violence partnered to produce the booklet, which provides whānau with important information about actions they can take to keep mokopuna safe.

Over 40,000 copies have now been printed and are distributed through health and social services and community groups, as well as Work and Income and Child, Youth and Family. The response from services and whānau has been very positive, particularly in relation to confronting head-on the difficult issue of child abuse and neglect in a way that doesn't minimise the strengths within whānau to address the risk factors.

"A first time grandmother was looking at the Aroha in Action booklet at the Women’s Refuge/It’s not OK campaign stand. She said ‘the other’ grandmother in the family kept saying that the new baby was being naughty.  She said she’d tried to tell her that babies can’t be naughty and now there it was in black and white in the Aroha in Action booklet.  'It’s wonderful.  It’s exactly what I need to help her understand.  It’s not just me saying it.' She took two copies." - Campaign team member.

## Hotspots

This section highlights objectives that are subject to variation or have been identified as areas of risk.  Objectives not mentioned in this section are on track to be completed as planned.

### Alerts

Table 1 highlights areas that have been identified as at risk of not being delivered as planned. Objectives for which a variation has been submitted are included in Table 2 below.

Table 1. Alerts

| Obj. | Title | Issue | Mitigation |
| --- | --- | --- | --- |
| 1.11 | New Migrant and Refugee Research Agenda | Delayed. Was due to be completed by April 2009. Clarification required on specific area the research activity will be focused on. | Further discussion with Taskforce members required. |
| 2.5 | Violence in the media | Deadline November 2009 | No update received. |

Table 1a highlights areas that have recently been identified as complete, have not proceeded or where the initiative has changed.  In some cases the reason the work has not proceeded is that they were the previous Government’s initiatives which are now being progressed in different ways.

Table 1a. Alerts

| Obj. | Title | Information | Status |
| --- | --- | --- | --- |
| 1.10* | Pacific Research Agenda (Ministry of Pacific Island Affairs (MPIA)) | Outcome and date change. MPIA is seeking to withdraw from this action, and focus on supporting the Pacific Programme of Action developed by the Pacific Advisory Group (PAG). | Note as withdrawn and consider removing from this Monitoring Report. Any new work can be reported through the new 2010 Taskforce work programme. |
| 2.1 | Kia Puäwai | Kia Puäwai was the previous Government’s initiative. This Government is giving priority to early intervention through the Drivers of Crime work programme which has different objectives. | Note as withdrawn and consider removing from this Monitoring Report. |
| 3.3* | Social Services Supporting Courts (Ministry of Social Development | Two of the Three objectives outlined have been completed. The third relates to the Community Link initiative that can be reported in the new Taskforce 2010 work programme. | Note as complete and consider removing from this Monitoring Report. Any new work can be reported through the new 2010 Taskforce work programme. |
| 4.1 | Maori Service Workforce Development | The objectives and actions outlined have been completed. | Note as complete and consider removing from this Monitoring Report. Any new work can be reported through the new 2010 Taskforce work programme. |
| 4.2* | Pacific Service Workforce Development (MSD) | This project was incorporated into the Pathway to Partnership work on workforce provider capacity and capability. | Note as withdrawn and consider removing from this Monitoring Report. |
| Action 43* (First Report) | Sharing information in a way that promotes the safety and well-being of victims and their families (Law Commission/ Privacy Commissioner) | This action is being led by the Law Commission and the Privacy Commissioner. The Law Commission released an issues paper - Review of the Privacy Act 1993 - in early March 2010. Submissions are requested by 30 April 2010. | Consider removing from the list of variations and from the work programme. |
| Action 62* (First Report) | Options to improve information-sharing between agencies and the District Court and the Family Court (MoJ) | Information-sharing is being considered as part of a wider review of the Domestic Violence Programmes Regime within the Domestic Violence Act and is included on the draft Taskforce 2010 work programme. | Consider removing from the list of variations and from this work programme and transfer to new 2010 Taskforce work programme. |
| Action 63* (First Report) | Simplify the application form for protection orders (MoJ) | Consultation with the NGO Alliance on 19 August 2009 and followed up in November 2009 confirmed that NGOs do not have concerns about the format of the protection order application forms. | Note as complete and consider removing from this Monitoring Report. |
| Action 64* (First Report) | Improve the use of security resources available to the courts (MoJ) | This work is now business as usual. MoJ will report in July 2010 about security incidents in domestic violence cases since the introduction of the new court security funding. | Note as complete and consider removing from this Monitoring Report. |
| Action 67* (First Report) | Develop options to ensure perpetrators attend and complete programmes (MoJ) | A review of the DV Programme regime including domestic violence “stopping violence” programmes is proposed as an item on the Taskforce’s 2010 work programme. | Consider removing from the list of variations and from this work programme and transfer to new 2010 Taskforce work programme. |

### *Noted in previous Monitoring Reports as variations.

### Upcoming Objective Deadlines (next two months)

This table highlights objective deadlines that are due over the next two months, or that have been completed and further deadlines need to be defined. If deadlines are not likely to be met, agencies should contact the Secretariat to discuss a possible variation.

Note there are no objectives due in the next two months.

## Variations

Variations are formal requests for changes to objectives and/or actions in the Taskforce’s Ongoing Programme of Action. The Taskforce approves major changes at Taskforce meetings. Variations are required for major changes, i.e. those that relate to the outcome of a piece of work, or the overall deadline for completion of the work. Any changes to key milestones will be flagged in the Monitoring Report.

Variation Request Process

The table below lists the variations that need to be discussed and agreed by the Taskforce at a future Taskforce meeting.

The majority of the variations have been moved to Table 1a as many of the objectives have been completed or have not proceeded where the initiative has changed.

Table 2. Variations yet to be approved.

| Obj. | Title (lead agency) | Due | Variation summary | Status |
| --- | --- | --- | --- | --- |
| 1.4 | Child Maltreatment | June 2009 | Delayed in some areas only. Extend to 30 June 2010. | Objective expected to be completed by 30 June 2010. |
| 1.7 | New Zealand Family Violence Clearinghouse (MSD) | June 2009 | The NZFVC sought approval via variation to initially extend the deadline to December 2011. This has been revised to July 2010. | Objective expected to be completed by 31 July 2010. |

Approved variations

This table includes all approved variations of objectives from the Ongoing Programme of Action.

Table 3. Approved Variations.

| Obj. | Title | Variation summary | Status |
| --- | --- | --- | --- |
| 2.4 | Curriculum Development (MoE) | The Objective remained the same, changes to the actions required. | Approved 28 March 2008. |
| 2.2 | Improving Attachment (MoH) | Scope and deadline changed, due to issues arising during the initial project scoping. New deadline of July 2010. | Approved 3 June 2009. |
| 2.5 | Violence in the Media (Families Commission) | Final deadline changed. A new deadline of November 2009. Objective and Actions will remain the same. | Approved 3 June 2009. |
| 3.3 | Social Services Supporting Courts (MoJ) | The Objective remained the same, changes to the actions required. | Approved 4 April 2008. |

Complete or removed objectives

The table below lists the objectives that have been removed from the Monitoring Report due to being completed, merging, or now being business as usual.

Table 4. Completed and Removed Objectives.

| Objective | Objective title | Reason for removal | Lead agency | Removed from which report |
| --- | --- | --- | --- | --- |
| 3.1 | Family Violence Courts | Complete. | MoJ | September 2009 |
| 1.8 | Case studies characterising good practice | Complete. | MSD | February 2009 |
| 2.7 | Family Violence Death Reviews | Complete. The Family Violence Death Review Committee will report regularly to the Government. | Ministry of Health (MoH). The Secretariat sits within MoH. | February 2009 |
| 4.3 | Service Demand Data | Complete. | MSD | February 2009 |
| 4.4a | Training our Staff | Combining Objective 4.4a into 1.5 was recommended as the two Objectives cover the same action and outcomes. | ACC | February 2009 |
| 1.1a | Mapping the Ongoing Programme of Action | Outcomes covered in Objective 1.1 through monitoring of the work of the Taskforce by the Secretariat. | Non-Government Organisations (NGOs) | November 2008 |
| 1.5 a, b & c | Family Violence Free Workplaces | Three sub-sections merged into one (Objective 1.5). | ACC, MSD and Police | First merged in November 2008 |
| 3.2 | Protocols for Family Violence Courts | Complete. | MoJ | November 2008 |
| 4.4b | Training of Staff (Child, Youth and Family (CYF)) | Business as usual, will be monitored within CYF. | CYF | November 2008 |

# Monitoring Report

The following section outlines progress on each key milestone and provides an update on work undertaken in the previous four months (December 2009 to March 2010) and work which is upcoming in the next three months (April 2010 to June 2010).

## Milestone updates and three month summaries

### Leadership

| 1.1 FACILITATION OF THE ONGOING PROGRAMME OF ACTION (OPOA) |
| --- |
| Lead agency | Taskforce Secretariat / All Taskforce agencies |
| Project Manager | Carra Hamon |
| First Programme of Action reference | Action 3 |
| Objective and actions (as per Work Programme) Facilitation, implementation and strategic engagement of the Ongoing Programme of Action for specific groups and across all sectors in New Zealand. Actions include: stewardship of the Ongoing Programme of Action work programme stewardship of children specific work programme stewardship of all other work programmes. |
| Objective deadline | Ongoing |
| Purpose To successfully monitor and ensure implementation of the Ongoing Programme of Action. |
| Key Milestones | Date | Description of Progress |
| 1.1.7 | Protection Orders update to be sent to Minister. | August 2010 | Next update to Taskforce in August 2010. |
| 1.1.18 | 9 December 2009 Taskforce meeting facilitated. | 9 December 2009 | Completed. |
| 1.1.19 | Facilitate additional meetings. | December, 2009. January, February, March 2010. | Organised meetings for Taskforce Priorities subgroup, Dashboard of Indicators subgroup, Taskforce Workshop and Taskforce Campaign subgroup. |
| 1.1.20 | Monitoring Report for March 2010 completed. | 14 April 2010 | Completed. |
| 1.1.21 | 28 April 2010 meeting facilitated. | 28 April 2010 | On track. |
| Progress to date (previous 4 months work) 9 December 2009 Taskforce meeting completed. 17 February 2010 Taskforce Priorities meeting completed. Meetings on the Dashboard of Indicators took place from November 2009 through to March 2010. 19 March 2010 Taskforce Workshop completed. Planning for 14 April 2010 Taskforce Campaign subgroup meeting on track. Planning for 28 April 2010 meeting on track. Current ongoing work (next 3 months) Preparing the Monitoring Report for the 28 April 2010 Taskforce meeting. Planning for 28 April 2010 Taskforce meeting. Planning for 14 April 2010 Taskforce Campaign subgroup meeting. Planning for 23 June 2010 Taskforce meeting. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 1.2 MĀORI PROGRAMME OF ACTION |
| --- |
| Lead agencies | Mäori Reference Group (MRG) Ministry of Social Development (MSD) |
| Contributors | Te Puni Kökiri (TPK), NGOs |
| Project Manager | Ann Dysart (MSD) |
| First Programme of Action reference | Action 7 |
| Objective and actions (as per Work Programme) A Programme of Action focused on eliminating violence in Mäori whänau is developed. Actions include: developing a Mäori Programme of Action (MPOA) ensuring the leadership and ownership of the actions at all levels of Te Ao Mäori ensuring all designated actions are monitored and achieved. |
| Objective deadline | June 2013. |
| Purpose To develop a process and plan that engages all areas of Te Ao Mäori in owning and addressing the issues of Family Violence and Child Abuse. To progress implementation of Mäori Reference Group’s (MRG) Action Plan in order to achieve zero tolerance of whänau violence. |
| Key Milestones | Date | Description of Progress |
| 1.2.6 | Whänau Ora Indicators | End of August 2010 End of Oct 2010 | Draft indicators identified Developing and testing indicator tool for whänau use Tikanga hui 2-3 days to look at the balance of what is tikanga in relation to women and children |
| 1.2.7 | Develop and publish initial Leadership Toolkit | June 2009 extended to September 2010 | Key work areas: Consolidate initial resources with reference to Whänau Ora service provision Work with key leaders to undertake trial |
| 1.2.8 | Develop positive messaging communications strategy | End of February 2010 | Key elements to messaging: Paid media: radio, print, resources, health TV. Resource Development: posters, pass along cards. Support NGOs: supplementary projects. All actions completed on time. |
| 1.2.9 | Development of media communication strategies | End of October 2010 | Future messaging Iwi Radio to develop their own strategies Production of information books on the remaining 5 themes |
| Background The MRG has developed an MPOA which was presented to the Taskforce. This contained a five year plan for 2008-2013, that was presented to and agreed by the Taskforce in August 2008. Progress to date (previous 3 months work) Developing Whänau Ora indicators using the findings from the completed hui and the work of the Whänau Ora Taskforce. Provide input into MSD policy and the work of the Taskforce member agencies i.e. TPK, Families Commission, MoJ, NZ Police. Providing TPK advice/support with Mäori research agenda and interviews for Case Studies. Launch of the Whänau Ora Taskforce Report 8 April 2010. E Tu Positive messaging development ongoing. E Tu Positive messaging underway on Iwi radio, giveaway newspapers, Mana magazine. Current ongoing work (next 3 months) Continue Whänau Ora leadership development. Continue cross-sector collaboration with key agencies that support Mäori-identified objectives. Continue to engage and support the work of whänau, hapu and iwi in ensuring leadership and change. Whänau Ora indicators. Continue Leadership Toolkit. Timing / Ongoing / Recommendations / Conclusions Status = on track and ongoing. |

| 1.3 PACIFIC PROGRAMME OF ACTION |
| --- |
| Lead agency | Pacific Advisory Group (PAG) Ministry of Social Development (MSD) |
| Contributors | Ministry of Pacific Island Affairs (MPIA), NGOs |
| Project Manager | Ann Dysart (MSD) |
| First Programme of Action reference | Action 7 |
| Objective and actions (as per Work Programme) A Programme of Action focused on eliminating violence in Pacific families is developed. Actions include: develop a Pacific Programme of Action (PPOA) hold discussions with agencies to confirm action areas of responsibility and process for implementation develop the leadership action area to be coordinated by MSD with PAG. |
| Objective deadline | June 2013 |
| Purpose To develop and implement a plan to address family violence within Pacific families. |
| Key Milestones | Date | Description of Progress |
| 1.3.9 | Develop resources for Pacific organisations, families and communities to increase awareness and understanding of causes and effects of family violence. | June 2010 | PAG developed a resource plan to determine priority resource materials for Pacific organisations. Priorities identified and have commenced development stage. Several PAG members are taking part in the development of resources (brochures and videos) for MoJ. |
| 1.3.10 | Facilitate opportunities to bring together Pacific community leaders to effect attitudinal and behavioural change. | June 2010 | On track. Dialogue is ongoing between Pacific leaders and Pacific Advisory Group. The PAG ‘Champions of Change Pacific Community Fono will be held in nine different cities nationwide from the end of April to early May 2010. At the fono, the pacific communities will be asked three specific questions; What are the solutions or community actions that will prevent family violence happening within pacific families? How will the pacific communities take leadership of these solutions to ensure actions are undertaken to prevent family violence within pacific communities? Who should take the leadership role and what would this look like? Outcome 1 – Practical community owned and driven solutions that work. Outcome 2 – Drawing the threads of what is common. Outcome 3 – Pooling all the success stories together to inform and create action. |
| 1.3.11 | Facilitate opportunities for dialogue between Pacific leaders and stakeholders and mainstream influencers to ensure Pacific communities are actively and consistently involved over the long term. | June 2010 | This milestone is due for completion in 2009/10 but work has commenced through initial discussions with MPIA on a communications strategy and process for implementation. Dialogue is ongoing between Pacific leaders and Pacific Advisory Group. The PAG community fono and summit will provide these opportunities and it’s envisaged that other ‘unknown opportunities’ will also be revealed. |
| Progress to date (previous 3 months work) Resource priorities identified and actions ongoing. Community engagement process has commenced. Discussions were held with other agencies to align their community engagement processes and to identify opportunities for joint venture projects. Advice provided to projects such as Community Response Fund, Child Maltreatment, Pacific Research Agenda and Family Violence Court Community Service. Current ongoing work (next 3 months) Continue with the development of identified priority resources. Follow through on the community engagement process. – The PAG community fono and national summit will be held in nine different cities around the country in late April and early May. The following are the dates and venues for these fono – Monday 26 April – West Auckland Tuesday 27 April – Central Auckland Wednesday 28 April - Waikato (Hamilton) Thursday 29 April - Hawke’s Bay (Hastings) Friday 30 April - Manawatu/Taranaki/Horowhenua (Palmerston North) Monday 3 May - South Auckland Tuesday 4 May - Wellington Wednesday 5 May - Christchurch Thursday 6 May - Dunedin Work with agencies to determine lead and supporting roles for the implementation of the Pacific Research Agenda work programme. Continue to provide advice to projects such as Community Response Fund, Break-away Holiday Programme Initiative, and the Campaign for Action on Family Violence. – Ongoing. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 1.4 CHILD MALTREATMENT |
| --- |
| Lead agency | Office of the Children’s Commissioner |
| Contributors | Ministry of Social Development (MSD), NGOs, NZ Police, Ministries of Justice, Health and Education |
| Project Sponsor | Dr John Angus |
| Project Manager | Pania Te Whaiti (MSD) |
| First Programme of Action reference | N/A |
| Objective and actions (as per Work Programme) The objectives of the second phase are to agree and then carry out the work programme. The work programme comprises an integrated, cross-sector approach to preventing child maltreatment. It draws on a growing evidence and knowledge base about the impacts of maltreatment. |
| Objective deadline | 30 June 2009 (second phase) |
| Purpose The Taskforce has agreed to give priority to the prevention of child maltreatment over the next three years, and has agreed the scope, focus and priorities of the proposed work programme. The purpose of the work for 2008 – 2009 is to: enhance the contribution of the health, education and social services sectors to prevention of child maltreatment understand better and take actions to reduce the incidence and prevalence of neglect, in particular of 0-5 year olds strengthen effective community responses. |
| Key Milestones | Date | Description of Progress |
| 1.4.7 | Project plans for the nine projects are completed. | September 2008 | Project plans for the five priority plans (1.4.8-9 and 1.4.12) are complete. Please see below for the remaining four project plans (‘Progress to date’). |
| 1.4.8 | Complete the review of the Health, Education and Social Service Sector Contributions to child maltreatment (3 of the 9 projects). | 31 March 2009 | All three reviews are completed. A summary of the findings will be presented in a report to the Taskforce at the December meeting. |
| 1.4.9 | Undertake research into neglect. | Delayed | Variation to be agreed to. The literature review is completed. The report back to the Taskforce is to be completed by 30 April 2010 (extended to June 2010) |
| 1.4.10 | Prepare advice on how development of the Campaign can further contribute to the prevention of child maltreatment. | 31 August 2008 | Complete to August 2008. |
| 1.4.11 | Develop the Campaign to include more specific actions on changing attitudes and behaviours around child abuse and neglect. | 30 June 2009 | Work completed. Twelve grants totalling $249,025 were given to recipients for child maltreatment prevention in the 2008/09 CAF funding round. |
| 1.4.12 | Take actions to work with communities to strengthen their preventive responses to child maltreatment including: gathering evidence on what works by 31 December 2008 providing greater support for successful community approaches by 31 March 2009 supporting philanthropic sector plans for a trial of new approaches and commencing an evaluation of any trial by 30 June 2009. | 30 June 2009 | Work completed. A summary of the four reports (Health, Education, Social Services Sector and Community Approaches) will be presented to the December Taskforce meeting. |
| Background The Ongoing Programme of Action includes developing a work programme on child maltreatment (including child sexual abuse) that: focuses on improving outcomes for children takes account of the different types of child maltreatment identifies priority areas where the Taskforce can make a difference. Progress to date (previous 3 months work) Reports on the findings and recommendations of the reviews of the Health, Education, Social Services Sector, and Community Approaches have been completed. Information from the sector reports has been used to provide advice to the Minister for Social Development and Employment in respect of her priority of preventing child maltreatment. Current ongoing work (next 3 months) The Neglect report is being finalised and expected to be available by June 2010 (deadline extended to 30 June 2010). A summary report has been circulated to Taskforce members, seeking agreement to recommendations. The Minister for Social Development and Employment has identified preventing child maltreatment as one of her top priorities. The information and recommendations from the reports will continue to be used in advice to the Minister. Timing / Ongoing / Recommendations / Conclusions Status = On Track. |

| 1.5 FAMILY VIOLENCE FREE WORKPLACES (MSD / ACC / NZ Police) |
| --- |
| Lead agency | Ministry of Social Development (MSD), Accident Compensation Corporation (ACC), NZ Police |
| Contributors | NGOs |
| Project Manager | David Dick (MSD), Maeve Agnew (ACC), Carol Train (NZ Police) |
| First Programme of Action reference | N/A |
| Objective and actions (as per Work Programme) Family Violence Free Workplaces (FVFW) are developed and implemented through HR policy; link to the Campaign, model for other agencies, role model for public and other workplaces. Actions include: developing policy putting in place tools and resources training contact people/family violence co-ordinators implementation developing a model for replication in the public sector and private sector. |
| Objective deadline | May 2012 |
| Purpose Family Violence Free Workplaces means staff in these workplaces are aware of and supported with family violence issues. These workplaces are expected to provide low cost, high impact prevention and recovery opportunities for members of the workplace who are affected by family violence. They may be victims, observers or perpetrators. Implementing FVFW is expected to decrease workplace stress and increase workplace productivity by empowering and supporting victims and observers of family violence and channelling perpetrators through appropriate channels to help them change their behaviour. |
| Key Milestones | Date | Description of Progress |
| 1.5.1 | Tools, resources and training to support, promote and raise awareness of stopping family violence are developed, agreed, and implemented as appropriate for each agency. | December 2009 | Complete. Ongoing activity. |
| 1.5.2 | Assess and evaluate agency programmes. | December 2010 | On track. |
| 1.5.3 | Develop a blueprint/model for implementing FVFW in public, private and non-government sectors. | June 2011 | On track. This Blueprint will be a collaborative piece of work between Police, MSD and ACC. |
| Context and background MSD, ACC and NZ Police have been working toward Objective 1.5 since the development and agreement of the Ongoing Programme of Action in late 2007. The three organisations meet regularly to work together, and share knowledge and learning. The collaboration reflects the overall objective of developing a Family Violence Free Workshops Blueprint that can provide a model for other organisations. Each agency began with plans to develop and implement guidance within their departments, to put into practice a range of initiatives to raise awareness of family violence, and provide support, information and assistance for staff who experience family violence. Each agency has taken different paths and learnt important lessons along the way that in some cases have resulted in initial plans and milestones being revised. These lessons, in addition to the various practical tools, training, procedures or policy relevant to each agency will inform the ‘blueprint’ that other organisations can consider as they develop their own approaches to Family Violence Free Workplaces. Completed work A range of initiatives have been implemented across ACC, MSD and NZ Police. The approach, implementation and timeframes within each agency differ but the key components are similar and have focused on planning, awareness raising, developing policy or guidance, training and the development of support and resources. Within each agency most of these initiatives are now part of ‘business as usual’ activity and are refreshed, promoted and reviewed on an ongoing basis. The activity completed includes: Tools and Resources: Planning - milestone development, communications plans, establishing internal working or reference groups, and establishing senior leadership and management support. Awareness raising - general awareness information sessions for staff; posters and booklets, staff calendars and other “promotional” material; visible promotions on organisational intranets or physical locations (lifts, foyers, staff rooms etc). Policy and/or guidelines - developed draft policy and/or implemented policy; developed guidance for managers. Support and resources - support package/toolkit developed for staff; resources and referral information published on agency intranets; peer support groups or other networks established or strengthened; ensured appropriate support and/or partnership arrangements through agency Employee Assistance Programme (EAP) providers. Training - in-depth family violence training (in conjunction with specialist providers such as Preventing Violence in the Home) for HR staff and/or peer support networks. Progress to date (previous 3 months work) Each agency continues to raise awareness of and promote its family violence policy/guidance and support resources for staff. An initial request for an EAP support service at NZ Police was approved by their Executive Committee on 16 November. A business case will now be written prior to commencing the tender process. Once the business case is signed off, communication and implementation of family violence employee support and EAP will commence. This will include the development of a tool kit for staff. ACC has begun a review of it’s internal provision of a separate Employee Assistance Programme for staff to access in regards to family violence issues. Due to limited usage and referral to appropriate external agencies for further support, ACC is reviewing whether this programme is effective. The initial review includes consideration of education and training for managers, and ease of access to appropriate external agencies to provide support for any staff member exposed to family violence. ACC will also review the internal communications process for our Family Violence Programme. The aim of this review is to update informative intranet pages where staff can access information on prevention and management options for family violence. Both pieces of work have begun, and General Manager endorsement is being sought. Current ongoing work (next 3 months) In line with agency priorities and communications plans each agency will continue to raise awareness of family violence and progress the development or revision of relevant guidance/policy and support resources. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 1.6 IWI-LED CRIME PREVENTION |
| --- |
| Lead agency | New Zealand Police |
| Contributors | Iwi, NGOs, Te Puni Kökiri (TPK), Ministry of Justice |
| Project Manager | TBC |
| First Programme of Action reference | N/A |
| Objective and actions (as per Work Programme) Iwi-led crime prevention plans which have a focus on the prevention of family violence. Actions include: provide support to Iwi to develop plans Iwi-led crime prevention strategies developed in accordance with each Iwi’s identified needs, values and timeframes Mäori Family Violence scoping studies. |
| Objective deadline | The NZ Police state that this is an iterative and evolving process that is being driven by Iwi. Precise deadlines are neither available nor appropriate at this stage. |
| Purpose In absolute numbers, a high number of Mäori churn through the criminal justice system every year. A new framework for action is being developed by Mäori with assistance from officials. That new framework is Iwi-led Crime Prevention Plans (ICPPs). ICPPs take a long-term, incremental approach to improving Mäori criminal justice outcomes. They are led by Iwi, with assistance from officials. |
| Key Milestones | Date | Description of Progress |
| 1.6.1 | Iwi populate their crime prevention plan templates. | Ngati Whatua me Tainui ki te Tonga, and, Ngai Tahu have set deadlines for first drafts of June 2009. | Writers appointed by Iwi are not using the template provided, so officials will condense and refine the core documents from Iwi into the template, once drafts are received. |
| 1.6.2 | Officials condense those templates into A3 summaries. | No deadline. | An A3 template has been designed to help structure thinking about solutions to agreed "problems" at the hui described in bullet point 7 below. |
| 1.6.3 | Summaries presented back to Iwi for confirmation. | No deadline. | Pending. |
| Background recent work (2007/2008) NZ Police have been supporting Iwi with the necessary tools to develop and design their own Plans. The type of support provided includes: providing Police intelligence to Iwi groups that enable Iwi to understand the crime problems and profiles of Mäori (offenders and victims) within their geographical areas providing specialised trained staff who are able to take Iwi through a formal problem solving approach to crime prevention, methodology training in SARA and POP problem-solving models providing draft ICPP templates and Guidance Notes for preparation of the Iwi Plans funding writers nominated by Iwi to begin drafting Iwi-specific crime prevention plans. Progress to date (previous 3 months work) Following the Iwi presentations to the special meeting of JSCEs, the lead for this work shifted from Police to MoJ. MoJ and TPK were to discuss the two existing plans with Ministers. It is not clear what the outcome was. Current ongoing work (next 3 months) TPK Auckland office has provided funding for a writer of the Ngati Whatua ICPP covering the Auckland Metro region. The writer has begun drafting their plan. NZ Police are assisting Iwi leaders to organise the first of a series of regional hui in Lower Hutt (April 2010) to discuss solutions to offending by Maori. Expected outputs include iwi-led crime and crash prevention plans in all regions in which hui are held, including action plans and a timetable for monitoring progress and an overarching strategy for reducing crime among Maori. Family Violence will be identified as a priority at the hui. Timing / Ongoing / Recommendations / Conclusions Status = Progress stalled over the past 3 months. But ICPPs are about to be reinvigorated through these series of regional hui. On track. |

| 1.7 FAMILY VIOLENCE CLEARINGHOUSE |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | Families Commission, NGOs |
| Project Manager | Desiree Brown |
| First Programme of Action reference | Actions 14 and 15 |
| Objective and actions (as per Work Programme) The New Zealand Family Violence Clearinghouse (NZFVC) is enhanced to ensure its efficacy and to become the independent, sustainable, comprehensive one-stop shop for national and international information on family violence. Actions include: develop a model and systems which optimise the operations of the NZFVC. |
| Objective deadline | June 2009 (Extend to December 2011 subject to variation requesting deadline change) |
| Purpose To review NZ Family Violence Clearinghouse activities and services and develop a strategy for moving forward. |
| Key Milestones | Date | Description of Progress |
| 1.7.2 | Scope redevelopment of NZFVC project, identify requirements and develop strategy. | September 2008 | Initial scoping work now complete. |
| 1.7.3 | Develop 2-5 year strategy. | Ongoing | Continue discussions around the new strategic plan and associated work programme. |
| 1.7.4 | Develop project plan and secure funding. | September 2008 | Complete. Cabinet funding is ongoing. |
| 1.7.5 | Implement new NZFVC website and service. | July 2010 | Delayed. Site now due to go live by July 2010. Delay due to contract negotiations and IT issues. (Subject to variation requesting final deadline change). |
| Progress to date (previous 3 months work) The operations of the NZFVC website are now in-house within MSD. Consultation with users and key stakeholders on requirements for the new NZFVC, and working with MSD IT on the information requirements and design. Current ongoing work (next 3 months) Regular meetings with the NGO consortium managers to discuss strategic direction for the NZFVC and continuing to consult with key stakeholders and advisory group members. Continued close working with MSD IT on information requirements and design. MSD IT has completed an IT options analysis which provides the basis of the IT business case for funding. Agreement on the capitalisation of redevelopment costs for the new website and associated applications has been approved by MSD IT. Now revisiting NZFVC website strategy to incorporate updated user needs and working with MSD IT to agree a substantive start date for the redevelopment. Working with NGO consortium to look at staffing requirements for the Clearinghouse moving forward. Role of NZFVC Project Manager to be renamed NZFVC Programme Manager and located with the Outreach Coordinator role in the NGO Consortium. This Programme Manager role will be advertised. Updating minor content on website so that it is ready for the transition to the new site. Working on processes/policies for the Clearinghouse moving forward. Appropriate contracting arrangements with NGO Consortium for after 30 June 2009 now being developed. New project manager assigned reflecting change in reporting lines at MSD. Timing / Ongoing / Recommendations / Conclusions Status = Delayed (Subject to variation requesting deadline change to June 2010). |

| 1.9 MĀORI RESEARCH AGENDA |
| --- |
| Lead agency | Te Puni Kökiri |
| Contributors | MRG, MSD, Families Commission, NGOs |
| Project Manager | Te Atarangi Whiu |
| First Programme of Action reference | New initiative |
| Objective and actions (as per Work Programme) Te Puni Kökiri has completed the first phase of this objective, that is, the development of a Mäori Research Agenda. Te Puni Kökiri is now undertaking the second phase which is to recommend further action. Improve our understanding of the nature of family violence in whänau Mäori and successful models of prevention and intervention. Actions include: review existing literature develop a research agenda link to the Taskforce strategic research agenda for family violence prevention recommend further action. |
| Objective deadline | A second phase is in development. |
| Purpose First phase purpose. To increase the evidence base by providing case studies of a minimum of three Mäori designed, developed and delivered programmes. Second phase purpose. To implement the Research Agenda through the establishment of a working group and the development of a Research Plan. |
| Key Milestones | Date | Description of Progress |
| 1.9.4 | Research Plan for the Mäori Research Agenda | June 2009 | Completed. Research Plan submitted to Taskforce in August 2009. |
| 1.9.5 | Establish Working Group | April 2010 | Currently working with representatives from the Families Commission, Ministry of Social Development, Ngā Pae o te Maramatanga and Health Research Council to progress the Agenda. Terms of Reference for Working Group have been developed. |
| 1.9.6 | Publish suite of Family Violence documents | May 2010 | Summative report to be published on TPK website May 2010. |
| 1.9.7 | Working Group Scoping Pape | June 2010 | Currently working with representatives from the Families Commission, Ministry of Social Development, Ngā Pae o te Maramatanga and Health Research Council to develop the Agenda. |
| 1.9.8 | Policy Research Report on Family Violence | June 2010 | On track. |
| Second Phase Te Puni Kökiri submitted the Research Plan to the Taskforce at their 5 August 2009 meeting. This output comprised: prioritisation of the Mäori Research Agenda to three key priorities proposed timeframes to complete the prioritised Mäori Research Agenda proposed Ministries and agencies responsible for completing the prioritised Mäori Research Agenda. The establishment of a Working Group, comprising government agencies and NGO representatives, is proposed to manage and coordinate the implementation of the prioritised Mäori Research Plan. The Working Group, through Te Puni Kökiri, will report to the Taskforce on progress of the implementation phase. Progress to date (previous 3 months work) The fact sheet has been published. Progressing the publication of the summative report on TPK website. Currently working alongside representatives from a number of government and non-government agencies to progress phase two. First draft of Policy Research Report completed. Current ongoing work (next 3 months) Publish remainder of phase one reports. Establish the Working Group. Implement research. Complete Policy Research Report. Timing / Ongoing / Recommendations / Conclusions Status = The second phase is underway and on track. |

| 1.10 PACIFIC RESEARCH AGENDA |
| --- |
| Lead agency | Ministry of Pacific Island Affairs (MPIA) |
| Contributors | PAG, MSD, Families Commission, NGOs |
| Project Manager | Liz Tanielu (MPIA) |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) Key stakeholders are being consulted over the variation to ensure agreement. The below Objective and actions are the original. |
| Improve our understanding of the nature of family violence in Pacific families and successful models of prevention and intervention. Actions include: review existing literature develop research agenda link to the Taskforce strategic research agenda for family violence prevention recommend further action. |
| Objective deadline | Final deadline to be confirmed (subject to variation). |
| Purpose To develop an understanding of Pacific family violence research priority topics and the issues which surround Pacific family violence research. |
| Key Milestones | Date | Description of Progress |
| 1.10.1 | Follow up PAG’s redrafted proposal for research work. | Sept 09 | Awaiting response from PAG on redrafted research proposal. |
| 1.10.2 | Meet with MSD and Families Commission to agree on direction for Pacific research work. | Oct 09 | A decision on next step has yet to be reached. Research opportunities are being explored. |
| Background As previously indicated, MPIA is not in a position to develop a research agenda but will work with the Ministry of Social Development and the Families Commission to identify the most relevant support that can be provided now. Such work may include the review of successful community led models to prevent family violence. The purpose will be to document and promote good Pan Pacific and ethnic specific models of prevention and intervention and examine ways in which government can support them to ensure sustainability. The recently released Family Violence Statistics Report prepared by the Families Commission will also inform this work. Progress to date (previous 3 months work) MPIA met with PAG and Families Commissioner Sandra Alofivae to discuss the variation and subsequent steps for the Research Agenda. It was agreed that PAG would revisit the intention behind the research agenda and re-draft the proposed requirements. Current ongoing work (next 3 months) Follow up PAG’s recommendations. Discuss and agree with MSD and Families Commission on research direction and respective roles and responsibilities. Timing / Ongoing / Recommendations / Conclusions Status = delayed. A variation presented 3 June to be agreed. |

| 1.11 NEW MIGRANT AND REFUGEE RESEARCH AGENDA |
| --- |
| Lead agency | Ministry of Social Development (MSD) |
| Contributors | NGOs |
| Project Manager | Dorothy Adams |
| First Programme of Action reference | N/A |
| Objective and actions (as per Work Programme) Improve our understanding of the nature of family violence in new migrant and refugee families and successful models of prevention and intervention. Actions include: review existing literature develop a research agenda link to the Taskforce strategic research agenda for family violence prevention recommend further action. |
| Objective deadline | April 2009 (extended to December 2010) |
| Purpose To develop an understanding of family violence and the issues which surround family violence in new migrant and refugee families. |
| Key Milestones | Date | Description of Progress |
| 1.11.2 | Scoping paper. | December 2008 | Complete. Draft research approach has been circulated internally for comment and feedback. |
| 1.11.3 | Recommendations for further action. | March 2009 | Delayed . Clarification from Taskforce members to be sought about what specific area they want to see research activity focused in. |
| Progress to date (previous 3 months work) Discussions with other agencies regarding priorities in this field of family violence prevention, and the research question this is intended to contribute towards, have taken place. Current ongoing work (next 3 months) It is proposed that before progressing a research agenda further, which will not deliver a specific research output, clarification be sought from the Taskforce. We need confirmation that it is a research agenda the Taskforce requires or that it would prefer to identify a specific area of focus for research activity that could be actioned. This would be a better use of currently limited resources. Timing / Ongoing / Recommendations / Conclusions Status = Delayed. |

| 1.12 ELDER ABUSE |
| --- |
| Lead agency | Ministry of Social Development/ Age Concern New Zealand |
| Contributors | NGOs |
| Project Manager | Cilla Corlett and Jayne McKendry |
| First Programme of Action reference | N/A |
| Objective deadline | 2010 |
| Purpose/Expected Outcome Complete, in consultation with the wider sector, a plan for further action on elder abuse and neglect, and implement the plan. The plan will include actions for: changing ageist attitudes and behaviours improving the social service sector’s responses to elder abuse and neglect improving the health sector’s responses to elder abuse and neglect preventing financial abuse of older people. |
| Key Milestones | Date | Description of Progress |
| 1.12.1 | Review draft plan for further action. | 30 October 2009 | Commenced. |
| 1.12.2 | Take to wider sector. | TBC |  |
| 1.12.3 | Implement plan. | TBC |  |
| Background We have completed the original objectives and actions for elder abuse (review existing literature; develop a research agenda; link to the Taskforce strategic research agenda for family violence prevention; and recommend further action). Over the past year, MSD and Age Concern NZ have been working on drafting a plan for further action on elder abuse and neglect, which we presented to the Taskforce in December 2008. The Minister for Social Development and Employment has since assigned Elder Abuse and Neglect Prevention as a “designated area of work” to the Minster for Senior Citizens, Hon John Carter. Progress to date (previous 3 months work) MSD and Age Concern have been reviewing the draft plan with the view to seeking Minister Carter’s agreement for us to take it to the sector to gain broader engagement with the plan. Current ongoing work (next 3 months) MSD and Age Concern will continue to review the draft plan. We will continue to report to the Taskforce on our progress. Timing / Ongoing / Recommendations / Conclusions Status = on track |

| 1.13 DATA ON NGO SERVICE DELIVERY |
| --- |
| Lead agency | Ministry of Social Development (MSD) |
| Contributors | NGOs, ACC, MoJ, Police, MoH |
| Project Manager | Dorothy Adams |
| First Programme of Action reference | NA |
| Objective and actions (from work programme) High quality data available about services delivered by, and the demand for, NGO and agency family violence services. Actions include: develop systematic and accurate data on services. |
| Objective deadline | Ongoing |
| Purpose To understand the family violence services available and the ongoing demand for services; both volume and type. |
| Key Milestones | Date | Description of Progress |
| 1.13.1 | Scoping project to understand what output from this project is going to add most value to relevant stakeholders. | 30 March 2009 | Identified key stakeholders. Have begun to meet with these stakeholders to understand requirements and what information is already available. |
| 1.13.4 | Project Plan, including identification of already existing data and resource implications, will be produced for further consultation. | 15 June 2009 | Delayed. Project currently being re-scoped. |
| Project re-scoping Note that this project is currently being re-scoped. This Objective will now not be as closely aligned with the Pathway to Partnership initiative. The outcome of the work will not change, however, milestones have been modified to reflect the redevelopment. Further milestones will be available once re-scoping is complete. Background Anecdotal evidence suggests the demand for Family Violence Prevention services is increasing. Considerable data exists about the services delivered by, and the demand for, NGO and agency family violence services but this information is not collected or collated in a systematic way so that any gaps can be identified and addressed. Current ongoing work (next 3 months) A stocktake of government funded family violence services contracted by MSD has been completed as part of the line-by-line review. There is also other work taking place on identifying government funded family violence services. Timing / Ongoing / Recommendations / Conclusions Status = delayed. While a stocktake of services is currently underway, data about the demand for services is not available from a single or comprehensive source. Applications to the Community Response Fund are likely to provide some of this information in the future. Once the full review of all family violence services is completed we will re-visit this action and re-scope as necessary. |

### Changing Attitudes and Behaviour

| 2.1 KIA PUĀWAI |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | All Taskforce members |
| Project Manager | Pania Te Whaiti |
| First Programme of Action reference | Not in first Programme of Action |
| Objective and actions (as per Work Programme) Kia Puäwai is supported in its implementation by the Taskforce. Taskforce supports initiatives such as: increasing coverage of intensive home visiting providing free Early Childhood Education for all vulnerable children aged 18 months – 3 years developing an integrated identification, assessment and referral system for young children expanding Early Years hubs and teen parent co-ordinators initiatives key workers to support at-risk families expanding Social Workers in Schools. |
| Objective deadline | Ongoing |
| Purpose This cross-agency initiative is building an early years intervention system to help ensure all children flourish in early childhood and reach their potential as young adults capable of developing healthy, respectful and violence-free relationships throughout their lives. |
| Key Milestones | Date | Description of Progress |
| 2.1.3 | B4School check pilot in place | Aug 2008 | Complete. Pilot in place. |
| 2.1.4 | Report-back to Cabinet | June 2009 | The report back to Cabinet has been replaced by the Cabinet paper on the Drivers of Crime. Cabinet agreed to a work stream on antenatal, maternity and early parenting support led by the Ministry of Health. |
| Progress to date (previous 3 months work) Kia Puäwai was the previous Government’s initiative. This Government is giving priority to early intervention through the Drivers of Crime work programme on antenatal, maternity and early parenting support which has different objectives and deliverables. Timing / Ongoing / Recommendations / Conclusions Status = Consider appropriateness of maintaining this work item in the Taskforce’s work programme. |

| 2.2 IMPROVING ATTACHMENT |
| --- |
| Lead agency | Ministry of Health / Auckland District Health Board |
| Contributors | MSD, ACC, MoE, NGOs |
| Project Manager | Pat Tuohy |
| First Programme of Action reference | N/A |
| Objective and actions (as per Work Programme) Promote and improve attachment between new-born babies and their parents and caregivers. Actions include: progress a pilot see how well it works report draw on key findings from parent support and development programmes already focused on supporting attachment between young children and their parents and caregivers. |
| Objective deadline | July 2010 |
| Purpose Supporting the promotion of healthy secure attachment in infants is important for the development of quality relationships between infants and parents and caregivers, and for its effect on human development and wellbeing. Promotion of secure attachment can be achieved through provision of information to parents, and support with strategies that enhance attachment and address any parenting concerns. Early intervention is recommended for infants of high-risk carers if developmental or behavioural problems are detected. |
| Key Milestones | Date | Description of Progress |
| 2.2.1 | Use of a new needs assessment and care planning process to allocate additional visits to support fathers and male partners, based on identified risk/need. | July 2010 | The pilot of the needs assessment and care planning process, including attachment and training will be under way by July 2010 |
| 2.2.2 | Promotion of infant-parent attachment and assessment of parent /child relationship difficulties as part of a new needs assessment and care planning process in the revised WellChild Framework. | July 2010 | The pilot of the needs assessment and care planning process, including attachment and training will be under way by July 2010 |
| 2.2.3 | Training for WellChild Providers to promote secure infant-parent attachment. | July 2010 | The pilot of the needs assessment and care planning process, including attachment and training will be under way by July 2010 |
| Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 2.3 CONDUCT DISORDER / SEVERE ANTI-SOCIAL BEHAVIOUR |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | MoE, MoH, MoJ and Police (Inter-Agency Plan partners). NGOs, Office of the Children’s Commissioner (OCC), and other relevant agencies will be consulted on policy development. |
| Project Manager | Phil Dinham |
| First Programme of Action reference | N/A |
| Objective and actions (as per Work Programme) Ensure comprehensive behavioural interventions for children aged 3-7 years with conduct problems and their families are delivered in accordance with the Inter-agency Plan by building on the specialist behavioural services already provided by the Ministry of Education. In addition, existing services for older children and young people will be transitioned to evidence-based, best-practice interventions. The Taskforce supports the four action areas in the Inter-Agency Plan: leadership, coordination, monitoring and evaluation transition existing service provision to evidence-based, best-practice interventions establish an intensive, comprehensive behavioural service for 3 -7 year olds build a shared infrastructure for the delivery of specialist behavioural services. |
| Objective deadline | 2012 |
| Purpose Developing and delivering a suite of services for the 5 per cent of early childhood and primary (and intermediate) school aged children who have conduct problems will reduce the prevalence of young people with these problems. Without appropriate interventions, these children are more at risk of becoming perpetrators of violence. Over time these services are anticipated to result in a subsequent reduction in cases of family violence. |
| Key Milestones | Date | Description of Progress |
| 2.3.3 | Agency service reviews/stocktake completed. | December 2008 | Initial stocktake completed. |
| 2.3.4 | Translating Evidence into Practice report (focus on 3-7 year olds’ services). | June 2009 | Completed. |
| 2.3.5 | Translating Evidence into Practice report (focus on adolescent services). | TBC | Advisory Group on Conduct Problems (AGCP) decided to defer completion of Adolescent report and prioritise the work on 8-12 year olds. |
| 2.3.6 | Translating Evidence into Practice report (focus on 8-12 year olds’ services). | July 2010 | AGCP has agreed to prioritise completing the report on 8-12 year olds by July 2010. |
| Ongoing deliverables to be aligned with Drivers of Crime work programme. |
| Background This is an inter-agency project which seeks to improve behavioural interventions for 0-17 year olds across service areas of the Ministries of Education, Health, Justice and Social Development (CYF). In particular, it will establish a comprehensive behavioural service for treating children aged 3-7 years (subject to further investment) and transition existing services for older children and young people to evidence-based, best-practice interventions. Progress to date (previous 3 months work) The AGCP Translating Evidence into Practice report (focus on 3-7 year olds’ services) has been published on the Ministry’s of Health and Education websites. Work is underway with the Ministry of Education’s Learning and Behaviour Action Plan to trial and evaluate the Incredible Years parenting programme for 3-7 year olds in the New Zealand context. The findings from the trial will inform any future investment in this area. AGCP has decided to defer completion of the Best Practice report for adolescents and prioritise completion of the Best Practice report for 8-12 year olds to July 2010. Current ongoing work (next 3 months) AGCP is progressing its report focusing on conduct problems services for 8-12 year olds. MSD, MoE and MoH are progressing implementation of a pilot study on the Incredible Years Basic Parenting Programme for 3-7 year olds in 3 research sites. Timing / Ongoing / Recommendations / Conclusions Status = on track, revised milestone dates deliverables to be confirmed. |

| 2.4 CURRICULUM DEVELOPMENT |
| --- |
| Lead agency | Ministry of Education (MoE) |
| Contributors | MSD (MYD), MoH, TPK, MPIA, OCC, NGOs |
| Project Manager | Chris Arcus |
| First Programme of Action reference | N/A |
| Objective and actions (as per Work Programme) Children and young people aged 5-18 years develop the knowledge and skills that they need to support good decision-making, to make healthy choices, and to seek help when they need it. Actions include: provide support to enable schools to develop their programmes within the National Curriculum (The New Zealand Curriculum for English medium, Te Marautanga o Aotearoa for Māori medium) to suit the diverse learning needs of their community strengthen whole-school strengths-based approaches that promote resilience and confidence in young people and those adults who support them seek opportunities to identify and respond to children who are affected by family violence. |
| Objective deadline | Ongoing |
| Purpose The purpose of education is to help children and young people reach their potential and develop the competencies they will need to live, learn, work and contribute as active members of their communities. Education contributes to the prevention and reduction of family violence in New Zealand communities by providing a safe environment that teaches and models skills to enable children and young people to manage their own wellbeing and to relate in healthy ways with others. It provides children and young people with the opportunity to learn skills they might not otherwise receive in the home environment. To experience the benefits of education, students must participate in and be engaged with the education system. The Ministry of Education supports educators to identify students who are at risk as a result of experiencing, witnessing or engaging in family violence and to work with parents, families and whānau, and other agencies to ensure these students are appropriately supported. |
| Key Milestones | Date | Description of Progress |
| 2.4.1 | Provide support to enable schools to develop their programmes in the National Curriculum (The New Zealand Curriculum (NZC) and Te Marautanga o Aotearoa) to suit the diverse learning needs of their community. Release final curriculum and supporting resources for schools to support the implementation of the curriculum. Professional leaders are supported to lead curriculum development, establish the conditions for professional learning and involve families / whānau in focusing on student achievement and educational outcomes based on the NZC. | Ongoing Ongoing | On track. The Ministry has continued to provide support for the ongoing implementation of the National Curriculum (Te Marautanga o Aotearoa for Mäori Medium and The New Zealand Curriculum for English medium). The Ministry continues to work with Iwi organisations to develop projects that will help them utilise both the New Zealand Curriculum and Te Marautanga o Aotearoa to develop a localised curriculum which reflects the skills and knowledge important to them. The Ministry has continued to plan and implement publication of exemplars of school community engagement and the development of school curriculum to meet the learning needs of student. Other curriculum advice and guidance continues to being published online and in print. |
| 2.4.2 | Strengthen the implementation of whole-school, strengths-based approaches that promote resilience and confidence in children and young people and those adults who support them. Support up to 730 teachers per year in developing effective teaching and leadership skills to support the implementation of school-wide approaches to student wellbeing / mental health. This involves strengthening teachers’ understanding of the connections between school organisation, curriculum design and delivery, and community consultation and partnerships. Identify successful professional learning approaches for teachers from the evaluation of the student wellbeing contracts and incorporate in the design and delivery of ongoing professional development contracts. | Ongoing Ongoing | In progress. The Taumata Whanonga – evidence to action summit was held in March 2009. The summit focused on establishing key actions required to improve support for children and young people with challenging behaviour. This included consideration of the links between behaviour, educational achievement and student and teacher well-being. Following the submission of an Action Plan to the Minister, further planning for effective implementation has continued. Contracts with current Student Well-being (SWB) and mental health providers were extended until December 2009. This year this work falls within the parameters of the Positive Behaviour for Learning Action Plan. The actions include ‘sustained professional development to provide the skills required to manage extreme behaviour’ and the ‘provision of evidence based whole-school programmes to achieve positive learning environment’. These were highlighted at the Taumata Whanonga. The school-wide implementation will begin in Term 2. A total of 400 schools will have engaged in this process by December 2014. Teachers will begin to engage in the Incredible Years teacher programme from the beginning of 2010. It is envisaged that by the end of 2014, 5,000 classroom teachers, early childhood teachers and resource teachers, learning and behaviour will have participated in the programme. |
| 2.4.3 | Seek opportunities to identify and respond to children and young people who are affected by family violence. Review the quality and accessibility of support available to educators who are concerned about children and young people affected by family violence. Develop a review of the support received by children and young people identified while at school as affected by family violence (in conjunction with Obj 1.4 Child Maltreatment). | Ongoing Ongoing | The education profile and plan guidelines and templates for children in care continue to be modified during trial sites throughout the country. A draft discussion document which presents findings from a stock-take of the Early Childhood Education’s contribution to ensuring the care and protection of children has been completed as part of the Child Maltreatment Prevention Work Programme. It is expected that this document will be released once the Taskforce has reviewed all sector reviews. |
| Background In 2002, the Ministry of Education’s Curriculum Stocktake Report identified that, while many students were achieving at world-class levels, there are wide disparities in outcomes for diverse students. Progress to date (previous 3 months work) 2.4.1 The National Curriculum Exemplars of effective curriculum development continue to be published online and in print. These are accompanied by guides to help schools apply lessons learned to their own situations. A range of other strategies including communications and in-school support continue to help schools develop their own curricula using the National Curriculum. 2.4.1 Te Marautanga o Aotearoa Te Marautanga o Aotearoa is in the final implementation phase and will complete in December 2010. From 2011, levels 1 and 2 Māori immersion schools are expected to implement their school based curriculum (marau-a-kura). Resources both online and in print continue to be developed to support Te Marautanga o Aotearoa. Professional development for in-service teacher educators (ISTEs) continues, to allow them to support schools to develop their marau-a-kura (school based curriculum) to reflect the skills, knowledge and aspirations of their community. 2.4.2 Whole-school, strengths-based approaches that promote resilience and confidence in children and young people Facilitators have continued to work with their contract schools to review progress towards meeting contract outcomes related to implementing school-wide approaches to student wellbeing and mental health. The Ministry of Education has continued to monitor data and progress by schools and data analysis has been used for the continuation of work in the participant schools. Following the Taumata Whanonga in March 2009, an Action Plan was submitted to the Minister of Education. The Minister has met with the sector stewardship group several times over recent months. This sector group is engaged in a positive way with the positive behaviour for learning action plan. Further planning for effective implementation is continuing. Contracts with current providers for Student Well-being and Mental Health (SWB) were extended until December 2009. 2.4.3 Identifying and referring children affected by family violence to appropriate services Modifications continue to be made to the template and guidelines being used in the trial sites throughout the country. A process evaluation of the trials by an independent researcher has been completed. Current ongoing work 2.4.1 Te Marautanga o Aotearoa Continued support of the implementation of Te Marautanga o Aotearoa through until December 2010 through the allocation of a national co-ordinator and 14 regional co-ordinators across the country to work in collaboration with other regionally-based In-Service Teacher Educators (ISTEs) to support schools within their regions. Case studies are being undertaken that look at how iwi and whānau are involved in school-based curriculum development in Māori medium education settings and what are the enablers and/or constraints to effective involvement. 2.4.2 Whole-school, strengths-based approaches that promote resilience and confidence in children and young people The Ministry of Education continues to work with representatives from the sector to confirm the implementation strategy for the Action Plan from the Taumata Whanonga held in March 2009. It is anticipated that the programme will be progressively implemented across schools, teachers and parents in 2010. The SWB contracts ended in December 2009. The outcomes associated with those contracts will be managed through the broader Positive Behaviour for Learning Action Plan. Over the next five years from 2010, a small number of programmes will be introduced across New Zealand. 2.4.3 Identifying and referring children affected by family violence Work will continue on the roll-out of the education profile and plan guidelines and template for children in care in trial sites throughout the country subject to funding from the Ministry of Health beyond June 2010. An independent evaluation of the trials has been completed. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 2.5 VIOLENCE IN THE MEDIA |
| --- |
| Lead agency | Families Commission |
| Contributors | NGOs |
| Project Manager | Radha Balakrishnan |
| First Programme of Action reference | Action 23 |
| Objective and actions (as per Work Programme) Variation to change deadline to November 2009 agreed 3 June 2009 Create awareness of the impact of violence in the media on children aged between 6 to 11 years. Actions include: scope an evidence-based public education and awareness programme aimed at parents scope financial implications develop an implementation plan. |
| Objective deadline | November 2009 |
| Purpose To scope a public education and awareness programme around violence in the media (its risks and impact) with an initial focus on parents of 6-11 year olds. |
| Key Milestones | Date | Description of Progress |
| 2.5.2 | Develop plan. | October 2008 | Planning work commenced. |
| 2.5.3 | Draft Report circulated for comment. | October 2009 | Commenced. |
| 2.5.4 | Report to the Taskforce. | November 2009 | On track. |
| Background The first Programme Of Action (POA) included an action to review how violence is portrayed in the media, utilising the 2004 Report on TV Violence in New Zealand, and to advise on implications for the Ongoing POA. The Taskforce supported raising awareness of the impact of violence within the media on children and young people. The 2004 report identified middle childhood (between 6-11 years) as a vulnerable age group and it was agreed that children in this group should be the initial focus of any public education work. A variation to extend the deadline to November 2009 was submitted, and was agreed by the Taskforce at the meeting on 3 June 2009. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 2.6 CAMPAIGN FOR ACTION ON FAMILY VIOLENCE |
| --- |
| Lead agency | MSD / Families Commission |
| Contributors | NGOs |
| Project Manager | Gael Surgenor (MSD) |
| First Programme of Action reference | Actions 29-39 |
| Objective and actions (as per Work Programme) Continue the Campaign for Action on Family Violence through: an advertising campaign resource development and distribution Community Action Fund projects. |
| Objective deadline | 30 June 2009 (Ongoing to 2010) |
| Purpose This is a community-based social marketing campaign which aims to influence the behaviour of target audiences, including perpetrators of family violence and their influencers. The programme is based on research into attitudes towards family violence and motivators and barriers to behaviour change. |
| Key Milestones | Date | Description of Progress |
| 2.6.5 | Administering a further round of the Community Action Fund to support local projects to support change at a local level. | June 2010 | Funding was provided to 49 community initiatives through CAF Round 4 (July/August 2009). Although there are no further CAF “Rounds” within the current time-limited budget, some recent or current successful projects have been extended. This will enable successful initiatives to be built on and activity to be increased to the end of June 2010 In December, funding to extend a number of Round 3 CAF projects was allocated to 10 projects. A small allocation was also provided for evaluation to be built into each project, which will provide useful information for future family violence prevention work. In January, extensions were negotiated to two more current projects and five more projects are currently being extended.. |
| 2.6.6 | Continue to support the messages of the television campaign during 2009/10 using the website, the 0800 information line and print resources. | June 2010 | On track. There were 431 calls to the 0800 line in December, 625 in January and 343 in February (increases occur when the advertising is on air). There were 14,083 visits to the website in January, 12,661 in February and 15,994 in March. |
| 2.6.7 | Continue a television advertising campaign addressing attitudes to family violence and intimate partner violence. | June 2010 | On track. The two current television advertisements went to air again in December 2009 and January 2010. Work is continuing on the third phase of mass media advertising. |
| 2.6.8 | Continue to build on the media advocacy work with the national news media to promote more responsible coverage of stories of family violence and provide training and support to enable community spokespeople to engage effectively with local media. | June 2010 | On track. Media training for community groups is completed, and training for new groups is provided as required. The key focus is now on working with the news media – to ensure accurate and effective reporting and to support the development of material and relationships for local newspaper campaigns. |
| 2.6.9 | Continue to identify and encourage Campaign ‘champions’ and spokespeople, to develop partnerships in business, sport and youth related organisations and to continue to seek opportunities for promotion within popular culture. | June 2010 | On track. Vic Tamati is continuing to speak around the country as a Campaign champion, and has been providing mentoring and support to fellow champions George Ashby and Tremain Mikaere (who appeared on Good Morning on TVNZ, interviewed by Brendon Pongia – who has expressed an ongoing interest. There is growing demand for all three to speak around the country. |
| 2.6.10 | Continue to measure the level of public awareness of the key messages of the Changing Attitudes and Behaviours Campaign. | Jun10 | On track. Four campaign-funded research and evaluation reports are about to be released. The reports are: An innovative approach to changing social attitudes around family violence in New Zealand: Key ideas, insights and lessons learnt. Report on giving, receiving and seeking help. Attitudes, Values and Beliefs Survey Report. Community Study Summary Report . The Reports are written for multiple audiences and will be shared with affiliated family violence prevention organisations and other government agencies, community groups, family violence prevention networks and organisations. |
| Background The Campaign for Action on Family Violence (the Campaign) is a four year campaign that calls on everyone to help put an end to family violence in New Zealand. The national campaign was launched with TV advertisements in September 2007. The Campaign message “Family violence – It’s not OK” has struck a chord with New Zealanders and has quickly become part of the kiwi vernacular. The Campaign is supported by a website, an 0800 Information Line and a Community Action Fund (CAF) that provides financial support for community-led activities. Progress to date (previous 3 months work) In February, the Nelson Mail newspaper decided to run a campaign on family violence in conjunction with a local poster campaign by the Nelson/Tasman Te Rito Network. The poster campaign will feature Chief Family Court Judge Peter Boshier and Clinical Psychologist Nigel Latta along with Nelson It's not OK Champion Tremain Mikaere. It will be launched just after a week long speaking tour of Nelson/Golden Bay by Vic Tamati. The It's not OK campaign will support the Nelson Mail by delivering a seminar on news reporting of family violence to Mail reporting staff and providing story ideas and stories for the paper. There is also some interest from the Rotorua Daily Post and the Northern Advocate (Northland) in delivering local family violemce campaigns. The campaign delivered a workshop on reporting on family violence to the Christchurch Press in February. The E Tu Whanau Ora media campaign launched the second theme, Whanaungatanga, in February. Print media placement included Mana magazine and community newspapers around the country, Two lots of advertisements played on iwi radio stations - 15 second sound bites and 90-second stories A number of new resources have been developed over the last few months: A new booklet, “Keeping Kids Safe and Secure”, provides information for families, friends, neighbours and workmates about the problems and situations that can lead to child abuse abuse and neglect. It explains how all of us can support families to prevent child abuse before it occurs and get help if it’s already happening. It was developed in consultation with a wide range of people who noticed that there is a lot of information out there about what to do if child abuse is suspected but very little about how to help prevent it happening in the first place. A toolkit for employers, “Good for Staff, Good for Business”, was released in March. A booklet has been printed which directs people to the “Are You Ok” website, where most of the material for businesses can be accessed. A new booklet on Giving Help Community Action Toolkit has been updated, and is close to completion. The Campaign is continuing to work with the Women’s Refuge in partnering with netball teams in order to gain reach into communities of young women and their families. We are currently talking to Netball New Zealand. Discussions are also underway with Sport Manukau. The Campaign continued to work with the youth initiative SAVE (Students Against Violence Everywhere), and worked with students in Nelson around the organisation of a national youth hui in March in Nelson. The Campaign also supported and attended a regional meeting of SAVE students in the Waikato . We are continuing to provide family violence training to local networks in response to demand. Three more training workshops on family violence prevention and a coordinated community response were delivered in February - in Motueka, Greymouth and Nelson (level 2) – and four in March – in Tauranga, Whanganui, Te Kuiti and Manukau. The Campaign partnered with Women’s Refuge at the three day Parachute music festival at Mystery Creek in Hamilton in January. The Refuge marquee was one of the busiest stands at the festival. The Aroha in Action resource (to help keep whänau safe through clear, accessible messages about keeping mokopuna safe from family violence) was particularly popular and staff handed out 7000 fans which included contact numbers for the It’s not OK helpline and Refuge services. Work continues to gain momentum with local government. The Campaign finalised partnership agreements with the Manukau City Council in January and the Hauraki District Council in February. Mayor John Tregidga is leading the local campaign with the Hauraki Family Violence Network. A Waihi-based project will look at alcohol and family violence through a town-wide campaign focussed on liquor stores and supermarkets, supported by local media, events and billboards. Upper Hutt City Council is nearing completion of a billboard campaign which will involve local sporting stars, rugby player Corey Jane and netballer Irene Van Dyk, both of whom live in the Upper Hutt district. Current ongoing work (next 3 months) Mass media and launch of phase 3 messaging and campaign: The next phase will move to giving and receiving help, focussing on the role of influencers and people’s close social networks. Formative research has been undertaken, and concepts have been developed and tested with a range of audiences (the research was undertaken by Phoenix Research with advice from Alison Town and Peter Adams). The concepts and results of the testing will be presented to the Taskforce Campaign subgroup on 14 April and the Taskforce on 28 April. Once the Taskforce and the Minister have given approval, production will commence. It is anticipated that the new phase will launch in June. Significant work will occur around the development of new material for the website and for print resources that support the third phase. We will also work with the helpline around information for helpers and influencers. Enrolling more local governments There will be a concentrated focus, in the next three months, on increasing the number of local government partnerships. Discussions are happening with Kapiti District Council and Dunedin City Council. Preliminary work is also underway with Christchurch City Council, Whangarei District Council, Opotiki District Council, South Wairarapa District Council, Nelson City Council, Whakatane District Council and Franklin District Council. The campaign team is working with Local Government New Zealand to publicise and promote the campaign work with local councils in an effort to attract more interest. This work will include a case study being written for the Local Government quarterly review, an article for the LGNZ fortnightly update and a presentation or presentations to the National Council or regional forum. Also, the local Government toolkit was finalised in February and will be launched and distributed in April. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

### Ensuring Safety and Accountability

| 3.3 SOCIAL SERVICES SUPPORTING COURTS |
| --- |
| Lead agency | Ministry of Social Development / Ministry of Justice |
| Contributors | Police, MWA, NGOs, ACC |
| Project Manager | Richard Joblin / Justine Cornwall |
| First Programme of Action reference | Action 52 |
| Objective and actions (as per Work Programme) A social services system modelled around family violence courts to support the courts by linking services to ensure victims and observers are kept safe, perpetrators are kept accountable and responsible, and families are assisted with their recovery needs. Actions include: introduction of Independent Victim Advocate / support person role in all Family Violence Courts introduce specialist enhanced case management staff in all Family Violence Courts referral and funding for non-mandated stopping violence programme providers for offenders. |
| Objective deadline | April 2009. Note that a variation has been drafted for Taskforce consideration. Responsibility for progressing the work on victim advocates was transferred to the Ministry of Social Development. |
| Purpose A social services system modelled around family violence courts to support the courts by linking services to ensure victims and observers are kept safe, perpetrators are kept accountable and responsible, and families are assisted with their recovery needs. |
| Key Milestones | Date | Description of Progress |
| 3.3.2 | Scoping and developing Family Violence Court Community Service (FVCCS), formerly called Independent Victim Advocate (IVA). | March 2009 | Delayed. Scoping and development of the FVCCS role has been completed. |
| 3.3.3 | Introduce specialist enhanced case management staff in all Family Violence Courts (FVCs). | TBC | No completion date confirmed as yet. |
| 3.3.5 | Consultation with other agencies and non-government organisations on the development of the role of the FVCCS. | February 2009 | Delayed. |
| 3.3.6 | The FVCCS will be rolled out in FVCs. | From Sept 2009 | Delayed. Funding for the FVCCS has been returned to the Crown and the initiative will not progress at this time. |
| Background The former Government announced that it would move towards fully funding actions 1 and 3 of this Objective from 2008/2009 (introduction of Independent Victim Advocate/support person role in all FVCs, and referral and funding for non-mandated stopping violence programme providers for offenders). Stopping violence programmes have been funded for defendants in the family violence courts since July 2008. Funding was not provided for Objective 2. Progress to date (previous 3 months work) The victim advocates funding has been returned to the Crown and this initiative will not progress at this time. MSD and MoJ are exploring other options to provide support to people affected by family violence who come into contact with the courts. Timing / Ongoing / Recommendations / Conclusions Status: Objective 1 – withdrawn. Objective 2. - MSD and MoJ are exploring options to provide support to people affected by family violence who come into contact with the courts. Objective 3 – completed. |

### Effective Support Services

| 4.1 MĀORI SERVICE WORKFORCE DEVELOPMENT |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | TPK, NGOs, MoE |
| Project Manager | Ann Dysart |
| First Programme of Action reference | Action 7 |
| Objective and actions (as per Work Programme) Mäori Service Workforce Development. Actions include: 60 Mäori trained to work with the Mauri Ora framework ongoing support of trained practitioners Jigsaw, Mäori Women’s Refuge and NNSVS (Toru Group) are undertaking work to revisit best practice with each organisation Toru Group is meeting to look at common issues and solutions. |
| Objective deadline | June 2009 |
| Purpose This proposal will allow for continued investment in the training and support of practitioners who work with Mäori whänau/communities where there is violence. |
| Key Milestones | Date | Description of Progress |
| 4.2.0 | Determine how to progress standards and learnings. | June 2009 | Gather data to support development of a progress plan. |
| 4.2.1 | Expansion of Training | June 2009 | Training has been undertaken in Tamaki Makaurau, Te Waipounamu, Waikato and Whanganui. |
| Current ongoing work (next 3 months) Monitor the programme as per contract requirements and make considerations when and if required. Expansion aimed at Apanui, East Coast, Whakaatu, Central North/Far North. Timing / Ongoing / Recommendations / Conclusions Status = completed. |

| 4.2 PACIFIC SERVICE WORKFORCE DEVELOPMENT |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | MPIA, NGOs, MoE |
| Project Manager | Richard Joblin |
| First Programme of Action reference | Action 7 |
| Objective and actions (as per Work Programme) Variation to adjust Objective deadline submitted. Pacific Service Workforce Development. Actions include: preparation of a project plan to guide workforce training and development in family violence services for Pacific families developing a long-term approach to NGO provider capability as this approach will support the development of Pacific family violence social service providers and workforce. |
| Objective deadline | July 2008 (Variation to change deadline submitted, not yet agreed). |
| Purpose This work will increase the quality and diversity of services working to eliminate family violence in the Pacific communities. This will include identifying the capacity and capability of this workforce and the avenues needed to further build and support Pacific People in working to stop family violence in Pacific Families. |
| Key Milestones | Date | Description of Progress |
| 4.2.2A | Changes have been made which have resulted in the remaining P2P funding being retained in Votes. | January 2011 | Government is currently considering decisions on uncommitted Pathways to Partnership funding. |
| New Action added Budget 2009 redirected $104,033 million towards a Community Response Contingency, which will be drawn upon for the Community Response Fund. Changes to the previous funding model are intended to ensure that funding for community-based social services more effectively support the sector through the current economic downturn. The new model will help position services to respond more effectively to the needs of families, children and young people when the economy emerges from the downturn. Current ongoing work (next 3 months) This work is subject to variation. Work is continuing on reviewing current investment in the capability of NGO social services. The Pacific service work force in family violence is included in this work focusing on increasing the quality and diversity of services working to eliminate family violence within Pacific communities. Government decisions are pending. Timing / Ongoing / Recommendations / Conclusions Status = delayed. Variation to change deadline submitted. |

# First Programme of Action update

Summary Analysis

The Taskforce for Action on Violence within Families’ (the Taskforce) first programme of action initially consisted of 76 actions which were developed from the Taskforce’s First Report. This was consolidated to 53 actions.

Of these 53 actions, 30 are complete. Work has commenced on another 13 actions and these are now either ongoing, business as usual, or are annual events. The remaining ten actions have been subsumed into the Ongoing Programme of Action and, along with other ongoing work, are now reported on, and monitored through, the regular Monitoring Reports provided to every Taskforce meeting.

Key to ‘Status’ column

Complete = Action complete. May have informed development of work in Ongoing Programme of Action.

OPOA = Work in these actions has been incorporated into the Ongoing Programme of Action, refer to Objective number.

Ongoing or Annual = Initial stage complete, currently Ongoing or business as usual. Some are Annual occurrences.

| # | Action | Agency | Information | OPOA # | Status |
| --- | --- | --- | --- | --- | --- |
| Leadership |
| 1 | Developing the next Programme of Action (POA) | All TF | OPOA released Feb 2008. | 1.1 | Complete |
| 3 | Successful implementation of POA | All TF | Incorporated into OPOA. | 1.1 & 1.1a | Complete, ongoing reporting |
| 7 | Drawing on Mäori and Pacific advisory groups | MSD | Representatives on Taskforce (TF), ongoing MRG and PAG meetings advise the TF. | Led to 1.2, 1.3, 1.6, 1.9, 1.10, 2.4, 4.1, 4.2 | OPOA |
| 8 | Incorporating migrant and refugee perspectives | MSD | Informed OPOA, also further research included in OPOA. | 1.11 | OPOA |
| 9 | Aligning business planning to reflect Taskforce vision | Sec. | SOIs to be regularly monitored. | 1.1 | Annual |
| 12 | Maintain overview of government strategies to ensure goals and activities are complementary with our work | All TF | Business as usual. Secretariat watching brief to ensure TF is aware of all relevant government strategies. All TF agencies info share on new strategies, and maintain overview of relevant government strategies. | 2.1 2.3 | Complete to date, Ongoing |
| 13 | Family Violence research strategy | FC | Initial report provided Oct 2007. Ongoing consultation with other research agendas. | Informs 1.9-1.12 Led to 1.13 | Ongoing |
| 14 | Monitoring the level of family violence in NZ | FC | Refer to Research Strategy, Action 13. | Led to 1.13 & 1.7 | Ongoing |
| 15 | Horizontal learning | MSD | Incorporated into OPOA. | 1.7 | OPOA |
| 19 | Evaluate the first POA | MSD | Ongoing actions from POA are updated in regular Monitoring Reports. | 1.1a | Complete |
| 21 | Families Commission research programme | FC | 3 year research complete. 21a Improving Family Violence surveillance data. 21b Elder abuse and neglect research – released Feb 2008. | Informed OPOA | Complete |
| 22 | ACC research programme | ACC | 22a Sensitive claims. 22b Effectiveness evaluation. 22c Whänau Ora research. 22d Evidence based guidelines. |  | Complete |
| Changing attitudes and behaviour |
| 23 | Review violence in media | FC | Informed development of 2.5 | 2.5 | Complete |
| 29 | Using research to guide Campaign strategy | MSD | The Campaign continues to 2010, with further development being guided by research and evaluation | 2.6 | OPOA |
| 35 | Campaign strategy | MSD / FC | As above | 2.6 | OPOA |
| 36 | Mass media campaign | MSD / FC | Phase one started Sept 2007, Phase two started Feb 2008. Both phase adverts repeated in 2008 and early 2009. | 2.6 | OPOA |
| 37 | Nurturing leaders… | MSD | Business as usual. Identified (and funded) through the Community Action Fund. | 2.6 | OPOA |
| 38 | Partnerships with NGOs | MSD/ FC | NGO groups are contracted to be funded for services. | P2P | Ongoing |
| 39 | Community Action Fund | MSD | 97 initiatives funded in first three rounds. Fourth round just announced and 49 initiatives approved. | 2.6 | OPOA |
| 40 | Building knowledge – media advocacy etc | MSD/ FC | 40a media advocacy – FACS. 40b FV awareness training – also led to 1.5. 40c Toolkit re-released. 40d White Ribbon day. | 2.6 2.6 1.5 2.6 - | OPOA OPOA OPOA Complete Annual |
| 4142 | Family violence death reviews | MoH | Family Violence Death Review Committee established, first report due mid 2009. | 2.7 | OPOA |
| Ensuring Safety and Accountability |
| 43 | Sharing information in a way that promotes safety and wellbeing | Previously MoJ | The Law Commission released an issues paper - Review of the Privacy Act 1993 in early March 2010. Submissions are requested by 30 April 2010. |  | Initial work complete, Ongoing |
| 44 | Family Violence victims know what support and services are available | MoJ | Communications material developed and distributed. Available on Family Court website. |  | Complete |
| 45 | Maximising safety factors when managing court rosters | MoJ | Security policy complete, sent to all courts as a circular in April 2008. |  | Complete |
| 46 | Increased thresholds for legal aid eligibility | MoJ | Thresholds increased. New legal aid regulations in force from March 2007. |  | Complete |
| 47 | Begin a review of legal aid remuneration rates | LSA | Review complete. Changes recommended. Budget 2008 approved 10% increase for 2008/2009. |  | Complete |
| 48 | Improving information courts provide about legal aid | MoJ | Info updated and provided in court info packs and in DV packs, Dec 2007. Court staff also provided with info for public enquiries. |  | Complete |
| 49 | Testing fixed fees for legal aid | MoJ / LSA | Testing complete. Three things were tested – fixed fees, the removal of prior approval requirements for standard family grants and proforma invoices. The removal of prior approval was implemented in October 2008 alongside revised family steps and disbursements. Fixed fees and proforma invoices are on hold. |  | Complete |
| 50 | Building safe and effective programmes for couples and families | MSD / MoJ | Service specifications set. MoJ in discussion with NZ Assoc of Counsellors. |  | Ongoing |
| 51 | Build capacity of interpreters in Courts | MSD / MoJ | More interpreters available in courts. Business as usual to continue building availability. |  | Complete |
| 52 | Investigate introduction of advocates in courts | MWA / MoJ / MSD | Investigation completed by MWA. Refer OPOA Objective 3.3 for further work. | 3.3 | Complete |
| 53 | Enhanced ability for courts to contact victims directly | MoJ / Police | Already possible, MoJ and Police will continue improving standardised process for CSV1 compliance and referral. |  | Complete |
| 54 | Review purchasing plans for programmes | MoJ | Reviewed. 2008 tender round complete. |  | Complete |
| 55 | Improve process for prosecutions for non-attendance at programmes | MoJ / Police | Memorandum of understanding between MoJ and Police for the transfer of prosecutions to Police signed. Transfer completed in June 2008. |  | Complete |
| 56 | Establish four additional Family Violence Courts | Judiciary / MoJ | Four established. Also Palmerston North (Sept 2008) and Whangarei (May 2009). | 3.1 | Complete |
| 57 | Family Violence Courts Evaluation | MoJ | Waitakere and Manukau evaluation complete. Released August 2008. | 3.2 | Complete |
| 58 | Forum to identify best practice for information exchange | MoJ | Held March 2007. Best practice ideas generated informed development of guidelines by agencies. |  | Complete |
| 60 | Enforcement of protection orders (POs) – police training, performance measures and policies | Police | Initiatives on addressing family violence “big picture” (which include POs) complete. Ongoing work includes: 60a Training 60b Performance measures 60c National investigation and prosecution policies. | Many & 4.4 | Complete. Ongoing work |
| 61 | Support and training for lawyers working in family violence-related areas | Judge Boshier | Workshops for FC lawyers done in 2007. Law Soc also produced a resource booklet. Similar training is likely to be ongoing. |  | Complete |
| 62 | Define options to improve information sharing between agencies and the Courts | MoJ | Information sharing is being considered as part of a wider review of the Domestic Violence Programmes regime within the Domestic Violence Act which is included on the draft Taskforce 2010 work programme. . |  | First stage complete Ongoing 2008 & beyond |
| 63 | Simplify application forms for Protection orders | MoJ | An information sheet on the Domestic Violence Act application process has been produced and is available online. Consultation with the NGO Alliance in August 2009 and followed up in November 2009 confirmed that NGOs do not have concerns about the format of the protection order application forms. |  | Completed . |
| 64 | Improve the use of security resources available to courts | MoJ | This work is business as usual for MoJ. |  | Complete |
| 65 | Consider an office to provide DVA-specific legal services | LSA MoJ | Currently developing objective and milestones as part of business planning. |  | Ongoing 2008 & beyond |
| 66 | Determine level of attendance and performance of perpetrators at programmes | MoJ | A report into the findings was completed on 30 September 2008 The results were to be fed into Action 67. |  | Complete |
| 67 | Develop options to ensure perpetrators attend and complete programmes | MoJ | A review of the Domestic Violence Programme regime including domestic violence “stopping violence” programmes is proposed as an item in the Taskforce’s 2010 programme of action. |  | Ongoing 2008/2009 & beyond |
| 68 | Information for perpetrators on programmes | Police | Information distributed. |  | Complete |
| 70 | Ensure the range of programmes matches the profiles of perpetrators | Corrections / MoJ | Options to potentially address gaps in programmes for prisoners with DV-related offences formulated. Corrections currently analysing these options. |  | Ongoing 2007/2008 & beyond |
| 71 | Local Case Collaboration (FVIARS) | CYF / Police | FVIARS nationwide roll-out complete. Now business as usual. | Informs 3.3 | Phase one complete, Ongoing 2008 & beyond |
| Effective Support Services |
| 72 | Govt investing $9 million over the next four years | MSD | 2006/2007 contracts and funding took place. Continued funding of contracts from baseline. |  | Develop-ment complete. Ongoing to 09/10 |
| 73 | Develop new funding model | MSD | Pathway to Partnership (P2P) developed and ongoing. $20.4 million allocated in 2007. $446 million announced 12 Feb 2008 to fund essential NGO child and family services. Community Response Fund announced May 2009. | 2.1/4.2 | Complete OPOA |
| 74 | Cost family violence and family support services | MSD | Costing tool developed as part of P2P as above. |  | Complete |
| 75 | Build on existing workforce and organisational development initiatives | MSD | Funding announced in 2008 and 2009 to build a sustainable NGO sector. Ongoing. | 2.1/4.2 | Develop-ment complete. Ongoing 2008 & beyond |
| 76 | Continue to promote the use of integrated contracts | MSD | Funding for Outcomes developed and implemented. These contracts now part of FACS core business under the Integrated Contracts team. |  | Complete |

# How this report works

The Ongoing Programme of Action Monitoring Report is organised into two sections:

- A summary section – which provides an overview of the key highlights over the previous two months, and identifies the hotspots that need to be monitored closely over the upcoming two months to ensure Objectives remain on track.

- A monitoring report section – which includes two key parts:

    - Summary information from the project plans for each Objective.

    - A summary of the progress of each Objective over the last three months and an overview of the work that is expected to occur over the next three months.

The Taskforce’s planning and reporting hierarchy consists of the following:

- Objectives – specific work that has been signalled in the programme of action

- Actions –  specific work signalled in the programme of action, as part of an Objective and/or in the Taskforce’s work programme which sits beneath the programme of action

- Key Milestones – taken from individual agency project plans.

There is also a formal variation process, which aims to:

- maintain the integrity of the Taskforce’s programme of action

- ensure there is transparent communication within the Taskforce about changes to Objectives and/or actions

- ensure the Objective and actions remain relevant to the Taskforce and its priorities.

A formal variation is required when a Taskforce agency wants to change an Objective, action or both. Formal variations are not currently required to change key milestones. However, any key milestone changes must be provided to the Secretariat and will be tracked in this Monitoring Report.

The variation template is attached to this report. An electronic copy can be obtained from the Taskforce Secretariat.

Reporting frequency

Ongoing Programme of Action Monitoring Reports will be produced for each Taskforce meeting. If a Taskforce meeting is changed to a workshop then a report will still be produced but will be circulated in hard copy only.

Other information

The information in the monitoring report centres on the key milestone information provided by each Taskforce agency.

To ensure the monitoring report remains current, as each milestone is reported complete it will be dropped from the report. The Secretariat will keep a record of all milestones so that this information can be used at a later date, if necessary.

| To | The Taskforce for Action on Violence within Families | Date |  |
| --- | --- | --- | --- |
| From |  |
| Security Level | In Confidence |
| Variation: request to amend Work Programme Objective |
| Action | For your approval |

I am seeking the Taskforce’s approval to change an Objective or action from the work programme for the Taskforce for Action on Violence within Families.

Current Deliverable:

[Insert Project / Work Programme Objective and/or Action]

[Insert current milestone/s (from project plan template)]

Changed to:

[Insert Project / Work Programme Objective and/or Action]

[Insert new milestone/s (also complete new project plan template)]

Reasons for a Variation Request

A variation to this deliverable has become necessary as:

- [please insert reason/s for variation]

Consultation

In seeking a variation to this deliverable, I have consulted and gained agreement from the following people:

| Name | Position and organisation |
| --- | --- |

Impact

The impacts in agreeing to this change are:

- [add details of any impact such as reporting to Cabinet, other key project timeframes, budget initiatives, reputation, legislation.]

The impacts in not agreeing to this change are:

- [add details of any impact such as reporting to Cabinet, other key project timeframes, budget initiatives, reputation, legislation.]

Recommendation

It is recommended that you:

- agree to a variation to an Objective or action found in the Taskforce’s work programme

[Insert Project / Work Programme Objective and/or Action]

[Insert new milestone/s (also complete new project template)]

Approve / Decline

| (Taskforce representative) |  |  |
| --- | --- | --- |
| (Taskforce agency) |  | Date |

| Peter Hughes |  |  |
| --- | --- | --- |
| Chair |  | Date |
| Approved ( Not Approved ( |